## ManPower ( Day) (hidden)
IZHAR CONSTRUCTION (PVT) LTD
MAF CARREFOUR, FORTRESS
Daily Manpower & Equipment Report
[7 empty] | Date: | 2008-12-05
(A) Manpower | [5 empty] | B) Equipment |  |  | No.
Position |  | No. | Position |  | No.
Project Manager |  | 1 | G Forman |  | 1 | Batching Plant |  |  | 1
Construction Manager |  | 2 | Carpenter Forman |  | 3 | Transit Mixer |  |  | 4
Planning Engineer |  | 1 | Carpenter |  | 13 | Excavator |  |  | 1
Asst. Planning Engineer |  | 1 | Carpenter Helper |  | 14 | Loader |  |  | 2
Site Engineers |  | 7 | Khalasi Foreman |  | 3 | Dewatering Pumps |  |  | 6
Safety Inspector |  | 1 | Khalasi |  | 35 | Tractor Trolley |  |  | 1
Safety Assistant |  | 4 | Khalasi Helper |  | 12 | Crane (20 T Capacity) |  |  | 1
Supervisor (Civil) |  | 20 | Mason |  | 22 | Roller |  |  | 1
Surveyors |  | 3 | Mason Helper |  | 4 | Floor Cutter |  |  | 3
Asst. Surveyors |  | 5 | Labor Mate |  | 10 | Drill Machine |  |  | 4
Lab Incharge |  | 1 | Labor |  | 133 | Generator Set |  |  | 5
Depty Lab Incharge |  | 3 | Welder |  | 9 | Water pump with Motors |  |  | 5
Accounts Officer |  | 1 | Surveyor Helper |  | 4 | Theodolite (Complete set) |  |  | 1
Asst. Accounts |  | 2 | G.Forman Brick & Plaster |  | 1 | Level Machine (Complete set) |  |  | 3
Admin Assistant |  | 1 | Electrician |  | 4 | Total Station (Complete set) |  |  | 1
Store Keeper |  | 1 | Electrician Helper |  | 2 | Plate compactor |  |  | 4
Assistant Store Keeper |  | 6 | Plumber |  | 1 | Jumper compactor |  |  | 3
Time Keeper |  | 3 | Plumber Helper |  | 1 | Electrical Grinder |  |  | 3
Camp. Boss |  | 1 | Generator Operator |  | 16 | Dumpers |  |  | -
Security Guard |  | 24 | Fabricator |  | 4 | Hilty |  |  | 1
Cook |  | 3 | Loader Operator + Helper |  | 2 | Screw gun |  |  | 2
Cook Helper |  | 0 | T.M Operator + Helper |  | 8 | Steel Bending Machine |  |  | 1
Mechanics |  | 1 | Plant Operator + Helper |  | 2 | Traller |  |  | -
Drivers |  | 3 | Excavator Operator + Helper |  | 2 | Welding Plants |  |  | 6
Steel fixer |  | 17 | Pump Operator + Helper |  | 0 | Steel Cutting Machine |  |  | 1
Office Boy |  | 7 | Roller Operator + Helper |  | 0 | Compressor Machine |  |  | 2
Work shop helper |  | 2 | Tractor Driver + Helper |  | 1 | Mixer Machine (1 load) |  |  | 4
Quantity Surveyor |  | 3 | Crane operator + Helper |  | 1 | Donkey pump |  |  | 7
Mechanical Forman |  | 1 | Forman |  | 15 | Rollar Compactor |  |  | 1
Trainee Supervisor |  | 3 | Labor / Helper |  | 191 | Lift Machine |  |  | 3
Purchaser |  | 1 | Steel Fixer |  | 17 | Mobile Concrete pump |  |  | 2
IT Administrator |  | 1 | Khalasi + Khalasi Helpers |  | 47 | Vibrator |  |  | 10
|  |  | Carpenter + Carpenter Helpers |  | 27 | 20 HP Turbine |  |  | 1
|  |  | Mason |  | 36
|  |  | Electrical Sub Contractor |  | 36
|  |  | HVAC Sub Contractor |  | 35
|  |  | Plumbing Sub Contractor |  | 13
|  |  | Izhar Steel |  | 16
|  |  | Fire Fighting |  | 11
|  |  | Curing Labor |  | 8
|  |  | Total Labor |  | 747 |  |  |  | Rain
Weather Condition
IZHAR CONSTRUCTION (PVT) LTD | [5 empty] | CONSULTANT
Signature : |  |  | Signature : |  |  | Signature :
Date: | 2008-12-05 |  | Date: | 2008-12-05 |  | Date:
Name: | Mr.Sohail Afzal |  | Name: | Mr.Muhammad Akram |  | Name: |  | Mr. Farooq Haider
Designation: | Project Manager |  | Designation: | Construction Manager |  | Designation: |  | Resident Engineer
12
11
10
9
8
7
6
5
4
3
2
1

## Manpower Report
LOGO |  | DAILY PROGRESS REPORT | [5 empty] | LOGO
Document No. |  | DD-RRR-DPR-002-R00 |  |  |  |  | Date | 2025-08-25
MANPOWER STATUS
Office Staff |  |  |  |  | Site Staff
Sr.No | Designation |  |  | Nos. | Sr. No | Designation |  |  | Nos.
1 | MEP Department |  |  | 4 | 1 | Site Engineer (Civil) & Supervisor |  |  | 2
[5 empty] | 2 | Surveyor, Asst. Surveyor & Helper |  |  | 1
[5 empty] | 3 | Lift Operator |  |  | 1
Total A |  |  |  | 4 | Total B |  |  |  | 4
Admin Staff / Store / Accounts |  |  |  |  | Skilled/Unskilled Manpower
Sr.No | Designation |  |  | Nos. | Sr. No | Designation |  |  | Nos.
[5 empty] | 1 | Sub Contractor |  |  | 2
[5 empty] | 2 | Masson |  |  | 2
[5 empty] | 3 | Labor |  |  | 1
[5 empty] | 4 | Helper |  |  | 0
[5 empty] | 5 | Carpentar |  |  | 2
[5 empty] | 6 | Carpentar Helper |  |  | 1
Total Admin Staff |  |  |  | 0 | Total C |  |  |  | 8
Grand Total (Daily Man Power)
Salaried Staff |  | 8 | Daily Wages |  | 0 |  | Sub-Contractor | 8
Grand Total Daily Manpower |  |  |  |  | 16 | Weather
Signature |  |  |  |  | Signature
Name: |  |  |  |  | Name:
Designation: Planning Engineer |  |  |  |  | Designation: Project Manager
Date: | 2025-08-25 |  |  |  | Date: | 2025-08-25
Formulas:
Designation = [Designation]

## Tools & Equipment
LOGO |  | DAILY PROGRESS REPORT | [6 empty] | LOGO
2025-08-25
TOOLS & EQUIPMENT STATUS
Tools & Equipment |  |  |  |  | Equipment Owned By |  | Status
Sr. No. | Description |  | Unit | Qty. | Company | Rental / Vendor | Store | Repair & Maintenance | Site Working
1 | Total Station Machine |  | No's | 0 | - | - |  |  |  | ü
2 | Auto-level |  | No's | 0 | - | -
3 | Wheel Barrow |  | No's | 0 | 2 | - |  |  | 2
4 | Dumper |  | No's | 0 |  | - |  |  | 0
5 | Road Roler Viberator |  | No's | 0 |  | - |  |  | 0
6 | Tractor |  | No's | 0 |  | - |  |  | 0
|  |  | At Store |  | Repair & Maintenance |  | Site Working
| 2023-08-26 |  |  |  |  | 2023-08-26
Formulas:
Rental / Vendor = [Description]

## Backup (hidden)
IZHAR CONSTRUCTION (PVT) LTD
CARREFOUR HYPERCENTER, FORTRESS, LAHORE
|  | Daily Manpower Strength | [8 empty] | Date: 5 Dec 08
A | Staff |  |  | B | Regular Workers |  |  |  |  | C | Daily Wages (Indirect Labor)
Sr.No | Title |  | Nos. | Sr.No | Title |  |  |  | Nos | Sr.No | Title |  | No.
1 | Project Manager |  | 1 | 1 | Security Guard |  |  |  | 24 | 1 | Electrician |  | 4
2 | Construction Manager |  | 2 | 2 | Cook |  |  |  | 3 | 2 | Electrician Helper |  | 2
3 | Planning Engineer |  | 1 | 3 | Cook Helper |  |  |  | 0 | 3 | Plumber |  | 1
4 | Asst.Planning Engineer |  | 1 | 4 | Mechanics |  |  |  | 1 | 4 | Plumber Helper |  | 1
5 | Site Engineers |  | 7 | 5 | Drivers |  |  |  | 3 | 5 | Fabricator |  | 4
6 | Safety Inspector |  | 1 | 6 | Sweeper |  |  |  | 1 | 6 | Cook Helper |  | 30
7 | Safety Assistant |  | 4 | 7 | Office Boy |  |  |  | 1 | 7 | Lab Helper |  | 1
8 | Supervisor (Civil) |  | 20 | 8 | LoaderOperator |  |  |  | 1 | 8 | Workshop helper |  | 2
9 | Surveyors |  | 3 | 9 | Loader Operator Helper |  |  |  | 1 | 9 | Office boy |  | 7
10 | Asst. Surveyors |  | 5 | 10 | T.M Operator |  |  |  | 5 | 10 | Generator operator |  | 16
11 | Lab Incharge |  | 1 | 11 | T.M Operator Helper |  |  |  | 3 | 11 | Steel fixer |  | 17
12 | Lab Technician |  | 3 | 12 | Plant Operator |  |  |  | 1 | 12 | Plant Helper |  | 4
13 | Accounts Officer |  | 1 | 13 | Plant Operator Helper |  |  |  | 1 | Sub total C |  |  | 89
14 | Asst. Accounts |  | 2 | 14 | Excavator Operator |  |  |  | 1
15 | Admin Assistant |  | 1 | 15 | Excavator Operator Helper |  |  |  | 1 | D | Daily Wages (Direct Labor)
16 | Store Keeper |  | 1 | 16 | Pump Operator |  |  |  | 0 | 1 | G Forman |  | 1
17 | Assistant Store Keeper |  | 6 | 17 | Pump Operator Helper |  |  |  | 0 | 2 | Carpenter Forman |  | 3
18 | Time Keeper |  | 3 | 18 | Civil Foreman |  |  |  | 0 | 3 | Carpenter |  | 13
19 | Camp. Boss |  | 1 | 19 | Electrician |  |  |  | 1 | 4 | Carpenter Helper |  | 14
20 | Quantity Surveyor |  | 3 | 20 | Tractor Driver |  |  |  | 1 | 5 | Khalasi Foreman |  | 3
21 | Asst.Project Coordinator |  | 0 | 21 | Tractor Driver Helper |  |  |  | 0 | 6 | Khalasi |  | 35
22 | Tranee supervisor |  | 2 | 22 | Crane operator |  |  |  | 1 | 7 | Khalasi Helper |  | 12
23 | Purchaser |  | 1 | 23 | Crane operator helper |  |  |  | 0 | 8 | Mason |  | 22
24 | Tranee Surveyor |  | 1 | 24 | Mechanical Forman |  |  |  | 1 | 9 | Mason Helper |  | 4
25 | IT Administrator |  | 1 | 25 | Electrical Supervisor |  |  |  | 3 | 10 | Labor Mate |  | 10
Sub Total A |  |  | 72 | Sub Total B |  |  |  |  | 54 | 11 | Labor |  | 133
[10 empty] | 12 | Welder |  | 9
[10 empty] | 13 | Welder helper |  | 4
Total (A+B+C+D) = |  | 486 | [7 empty] | 14 | Surveyor Helper |  | 4
[10 empty] | 15 | G.Forman Brick & Plaster |  | 1
[10 empty] | 16 | Plant Helper |  | 1
[10 empty] | 17 | Sweeper |  | 2
[10 empty] | Sub Total D |  |  | 271
Sr.No | Subcontractor Name | Job |  |  | Forman | Labor | Steel Fixer |  | Khalasi |  | Carpenter | Mason | Total
1 | Haji Riaz | Shuttering |  |  | 1 | 0 | 0 |  | 6 |  | 3 | 0 | 10
2 | Mehmood Masih | Massonary |  |  | 1 | 15 | 0 |  | 0 |  | 0 | 10 | 10
3 | Abdul Majeed | Massonary |  |  | 1 | 6 | 0 |  | 0 |  | 0 | 6 | 20
4 | Muhammad Rafiq | Steel fixer |  |  | 1 | 4 | 10 |  | 0 |  | 0 | 0 | 15
5 | Muhammad Riaz | Steel fixer |  |  | 1 | 6 | 0 |  | 0 |  | 0 | 10 | 17
6 | Muhammad Akram | Excavation |  |  | 1 | 7 | 0 |  | 0 |  | 0 | 0 | 8
7 | Fareed Khan | Excavation |  |  | 1 | 19 | 0 |  | 0 |  | 0 | 0 | 20
8 | Nazir Ahmad | Excavation |  |  | 1 | 15 | 0 |  | 0 |  | 0 | 0 | 16
9 | Aslam Shah | Concrete |  |  | 1 | 14 | 0 |  | 0 |  | 0 | 5 | 20
10 | Ijaz Butt | Road work |  |  | 1 | 5 | 0 |  | 0 |  | 0 | 0 | 6
11 | Muzzamal Mushtaq | Plumbing |  |  | 1 | 6 | 0 |  | 0 |  | 0 | 0 | 7
12 | Muhammad Ishaq | Dismantelling |  |  | 1 | 10 | 0 |  | 0 |  | 0 | 5 | 5
13 | Izhar Steel | Steel works |  |  | 1 | 15 | 0 |  | 0 |  | 0 | 0 | 16
14 | Electrical | Electrical |  |  | 1 | 35 | 0 |  | 0 |  | 0 | 0 | 36
15 | HVAC | HVAC works |  |  | 1 | 34 | 0 |  | 0 |  | 0 | 0 | 35
16 | Ejaz | Column
17 | Fire Fighting | Fire works |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
18 | Piping Team | Piping Works |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
19 | Ducting Team | Duct Works |  |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Total |  |  |  |  | 15 | 191 | 10 |  | 6 |  | 3 | 36 | 261
| Grand Total (A+B+C+D+E) = |  |  | 747
| Time Keeper |  |  | Adim Assistant |  |  |  | CM |  |  |  | PM

## Progress
LOGO |  | DAILY PROGRESS REPORT |  |  |  |  | LOGO
PROGRESS OVERVIEW
Work Done for Previous Day | [6 empty] | 2025-08-24
Sr. No. | Activity |  | Location / Grid | Unit | Qty. | Completed % | Remarks
1 | Plaster works |  | Class Room 1 |  |  | 100%
2 | Plaster works |  | Class Room 2 |  |  | 100%
3 | Plaster works |  | Class Room 3 |  |  | 100%
4 | Plaster works |  | Class Room 4 |  |  | 100%
5 | Electrical Work (Jari Work) |  | Class Rooms |  |  | 100%
6 | Electrical Work (Conduiting) |  | Class Rooms |  |  | 100%
7 | Electrical Work (Cabling ) |  | Class Rooms |  |  | 30%
2025-08-25
| Activity |  | Location | Unit | Qty. | Completed % | Remarks
1 | Electrical Work |  | Class Rooms
2 | Tile Work
3
4
BOTTLE NECKS :
2023-08-26

## Pictorial Progress
LOGO | DAILY PROGRESS REPORT | LOG
PICTORIAL PROGRESS REPORT |  | 2025-08-25
Plastering of Flooring in Progress
Curring of Plastering Work
Preparation of Plaster Work after Mesh Fixing
Checking the Floor Plaster Level
Brickwork at Class Room -1
Electrical Work (Wall Conduiting) in Progress