## Frame Structure
Project Status Sheet
Project Name :
Date | 2025-07-20
Sr. No. | Description | Block - AB | Block - C
Frame Structure Works |  | Completion % | Completion %
1 | Earthworks & Surface Preparation | 50% | 100%
2 | Raft (-9'7") | 100% | 100%
3 | Ground Floor Slab (+2'00") | 100% | 100%
4 | 1st Floor Slab (+17'00") | 100% | 100%
5 | 2nd Floor Slab (+32'00") | 100% | 100%
6 | 3rd Floor Slab (+44'00") | 100% | 100%
7 | 4th Floor Slab (+56'00") | 100% | 100%
8 | 5th Floor Slab (+68'00") | 100% | 100%
9 | 6th Floor Slab (+80'00") | 100% | 100%
10 | 7th Floor Slab (+92'00") | 100% | 100%
11 | 8th Floor Slab (+104'00") | 100% | 100%
12 | 9th Floor Slab(+116'00") | 100% | 100%
13 | 10th Floor Slab (+128'00") | 100% | 100%
14 | 11th Floor Slab (+140'00") | 100% | 100%
15 | Roof Slab(+152'00") | 45% | 100%
16 | Mumty (+160'00") | 60% | 100%

## Grey,Finshing &Facade
Project Status Sheet
Project Name :
Date | 2025-07-20
Sr. No. | Description | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor | 4th Floor | 5th Floor | 6th Floor | 7th Floor | 8th Floor | 9th Floor | 10th Floor | 11th Floor | Rooftop
A | Finishing & MEP Works
1 | R.C.C. Frame Structure | 100% | 100% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Block Masonry Works | 100% | 100% | 60% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Plastering Works | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | PCC Flooring | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Floor & Wall Tiling & Marble Works | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | False Ceiling Works | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Paint Works (2 Coats) | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Installation of Doors, Cabinets & Wardrobes | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Railing Works | 100% | 100% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Aluminium & Glazing Works | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Paint Works (Final Coat) | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 90% | 90% | 100% | 100% | 100% | 100% | 100%
14 | Water Proofing Works | 100% | 60% | 100% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
B | MEP
| Distribution Board | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Wall Embedded Services (PVC Conduit, Backboxes, PPRC Pipe) | 100% | 100% | 100% | 92% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Floor Embedded Services (MEP) | 100% | 100% | 100% | 80% | 100% | 92% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Overhanging MEP Services (WS, SS, EW,ELV, CT) | 100% | 100% | 100% | 100% | 100% | 93% | 60% | 80% | 90% | 90% | 90% | 90% | 90% | 90%
| Installation of MEP Fixtures | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
C | Façade Works
16 | External Plaster |  | 100% | 100% | 100% | 80% | 50%
17 | MEP Works |  | 90% | 60% | 50% | 80% | 50%
18 | Travertine Works |  | 90% | 70% | 100% | 80% | 50%
19 | Paint Works |  | 90% | 80% | 100% | 80% | 100%

## ,Finshing &Facade
Project Status Sheet
Project Name :
Date | 2025-07-20
Sr. No. | Description | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor | 4th Floor | 5th Floor | 6th Floor | 7th Floor | 8th Floor | 9th Floor | 10th Floor | 11th Floor | Rooftop
A | Finishing & MEP Works
1 | R.C.C. Frame Structure | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Block Masonry Works | 100% | 100% | 100% | 100% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 80% | 0%
4 | Plastering Works | 75% | 100% | 100% | 100% | 82% | 82% | 82% | 82% | 80% | 80% | 85% | 75% | 5% | 0%
5 | PCC Flooring | 65% | 100% | 100% | 100% | 100% | 75% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | Floor & Wall Tiling & Marble Works | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | False Ceiling Works | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | Paint Works (2 Coats) | 0% | 100% | 100% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | Installation of Doors, Cabinets & Wardrobes | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | Railing Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | Aluminium & Glazing Works | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | Paint Works (Final Coat) | 0% | 100% | 100% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | Water Proofing Works | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
B | MEP
15 | Distribution Board | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
16 | Wall Embedded Services (PVC Conduit, Backboxes, PPRC Pipe) | 90% | 100% | 100% | 100% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 25% | 0%
17 | Floor Embedded Services (MEP) | 90% | 100% | 100% | 100% | 80% | 80% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
18 | Overhanging MEP Services (WS, SS, EW,ELV, CT) | 24% | 100% | 100% | 50% | 30% | 30% | 30% | 28% | 24% | 24% | 24% | 1% | 0% | 0%
19 | Installation of MEP Fixtures | 0% | 100% | 100% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C | Façade Works
20 | External Plaster |  | 100% | 100% | 100%
21 | MEP Works |  | 100% | 100% | 50%
22 | Travertine Works |  | 100% | 100% | 100%
23 | Paint Works |  | 100% | 100% | 100%

## Status- Sheet 1
Project Status Sheet
Project Name :
Date | 2025-07-20
Sr. No. | Description | Basement | Ground Floor | 1st Floor | 2nd Floor | 3rd Floor | 4th Floor | 5th Floor | 6th Floor | 7th Floor | 8th Floor | 9th Floor | 10th Floor | 11th Floor | Rooftop
A | Finishing & MEP Works
1 | Block Masonry Works | 100% | 100% | 100% | 100% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 80% | 0%
2 | Wall Embedded Services (PVC Conduit, Backboxes, PPRC Pipe) | 90% | 100% | 100% | 100% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 25% | 0%
3 | Distribution Board |  | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
4 | Plastering Works | 75% | 100% | 100% | 100% | 82% | 82% | 82% | 82% | 80% | 80% | 85% | 75% | 5% | 0%
5 | Floor Embedded Services (MEP) | 90% | 100% | 100% | 100% | 80% | 80% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | PCC Flooring | 65% | 100% | 100% | 100% | 80% | 65% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | Overhanging MEP Services (WS, SS, EW,ELV, CT) | 24% | 100% | 100% | 100% | 30% | 30% | 30% | 28% | 24% | 24% | 24% | 1% | 0% | 0%
8 | Floor & Wall Tiling & Marble Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
9 | False Ceiling Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | Paint Works (2 Coats) | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | Installation of Doors, Cabinets & Wardrobes | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
11 | Installation of MEP Fixtures | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | Railing Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
13 | Aluminium & Glazing Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
14 | Paint Works (Final Coat) | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
15 | Water Proofing Works | 0% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
B | Façade Works
16 | External Plaster |  | 100% | 100% | 100%
17 | MEP Works |  | 100% | 100% | 100%
18 | Travertine Works |  | 100% | 100% | 100%
19 | Paint Works |  | 100% | 100% | 100%