## WBS (hidden)
wbs_id | name | Level | Order | Path | Project_ID
28990 | Office Building Works | 1 | 1 | 28989¦28990 | 4654
28991 | Project Start / Initation Phase | 2 | 2 | 28989¦28990¦28991 | 4654
28998 | Letter of Award | 3 | 3 | 28989¦28990¦28991¦28998 | 4654
28999 | Kick of Meeting | 3 | 4 | 28989¦28990¦28991¦28999 | 4654
29000 | Project Milestones | 3 | 5 | 28989¦28990¦28991¦29000 | 4654
29001 | Start Milstones | 4 | 6 | 28989¦28990¦28991¦29000¦29001 | 4654
29002 | Finish Milstones | 4 | 7 | 28989¦28990¦28991¦29000¦29002 | 4654
29003 | Payment Milstones | 4 | 8 | 28989¦28990¦28991¦29000¦29003 | 4654
29004 | Moblization Phase | 3 | 9 | 28989¦28990¦28991¦29004 | 4654
29005 | Labor Resoures | 4 | 10 | 28989¦28990¦28991¦29004¦29005 | 4654
29006 | Non-Labor Resources | 4 | 11 | 28989¦28990¦28991¦29004¦29006 | 4654
28992 | Documnets Submission Phase | 2 | 12 | 28989¦28990¦28992 | 4654
29007 | Preparation & Submission | 3 | 13 | 28989¦28990¦28992¦29007 | 4654
29008 | Approval | 3 | 14 | 28989¦28990¦28992¦29008 | 4654
28993 | Engineering & Design Phase | 2 | 15 | 28989¦28990¦28993 | 4654
29009 | Coceptual Design | 3 | 16 | 28989¦28990¦28993¦29009 | 4654
29011 | Preparation & Submission | 4 | 17 | 28989¦28990¦28993¦29009¦29011 | 4654
29012 | Approval | 4 | 18 | 28989¦28990¦28993¦29009¦29012 | 4654
29013 | Detailed Design | 3 | 19 | 28989¦28990¦28993¦29013 | 4654
29014 | Sub-Structure | 4 | 20 | 28989¦28990¦28993¦29013¦29014 | 4654
29015 | Preparation & Submission | 5 | 21 | 28989¦28990¦28993¦29013¦29014¦29015 | 4654
29016 | Approval | 5 | 22 | 28989¦28990¦28993¦29013¦29014¦29016 | 4654
29017 | Super Structure | 4 | 23 | 28989¦28990¦28993¦29013¦29017 | 4654
29018 | Preparation & Submission | 5 | 24 | 28989¦28990¦28993¦29013¦29017¦29018 | 4654
29019 | Approval | 5 | 25 | 28989¦28990¦28993¦29013¦29017¦29019 | 4654
29020 | Electrical | 4 | 26 | 28989¦28990¦28993¦29013¦29020 | 4654
29021 | Preparation & Submission | 5 | 27 | 28989¦28990¦28993¦29013¦29020¦29021 | 4654
29022 | Approval | 5 | 28 | 28989¦28990¦28993¦29013¦29020¦29022 | 4654
29023 | Mechanical Drawings | 4 | 29 | 28989¦28990¦28993¦29013¦29023 | 4654
29024 | Preparation & Submission | 5 | 30 | 28989¦28990¦28993¦29013¦29023¦29024 | 4654
29025 | Approval | 5 | 31 | 28989¦28990¦28993¦29013¦29023¦29025 | 4654
29027 | Plumbing Drawings | 4 | 32 | 28989¦28990¦28993¦29013¦29027 | 4654
29028 | Preparation & Submission | 5 | 33 | 28989¦28990¦28993¦29013¦29027¦29028 | 4654
29029 | Approval | 5 | 34 | 28989¦28990¦28993¦29013¦29027¦29029 | 4654
29031 | Fire Network Drawings | 4 | 35 | 28989¦28990¦28993¦29013¦29031 | 4654
29032 | Preparation & Submission | 5 | 36 | 28989¦28990¦28993¦29013¦29031¦29032 | 4654
29033 | Approval | 5 | 37 | 28989¦28990¦28993¦29013¦29031¦29033 | 4654
28994 | Procurement Phase | 2 | 38 | 28989¦28990¦28994 | 4654
29034 | Local Purchase | 3 | 39 | 28989¦28990¦28994¦29034 | 4654
29035 | Forign Procurement | 3 | 40 | 28989¦28990¦28994¦29035 | 4654
29036 | Longlead Items | 3 | 41 | 28989¦28990¦28994¦29036 | 4654
28995 | Construction Phase | 2 | 42 | 28989¦28990¦28995 | 4654
29037 | Civil Works | 3 | 43 | 28989¦28990¦28995¦29037 | 4654
29038 | Sub-Structure | 4 | 44 | 28989¦28990¦28995¦29037¦29038 | 4654
29039 | Excavation | 5 | 45 | 28989¦28990¦28995¦29037¦29038¦29039 | 4654
29040 | Foundation | 5 | 46 | 28989¦28990¦28995¦29037¦29038¦29040 | 4654
29041 | Super Structure | 4 | 47 | 28989¦28990¦28995¦29037¦29041 | 4654
29042 | Coulmn & Beams | 5 | 48 | 28989¦28990¦28995¦29037¦29041¦29042 | 4654
29045 | Slab Works | 5 | 49 | 28989¦28990¦28995¦29037¦29041¦29045 | 4654
29044 | Masonary Works | 5 | 50 | 28989¦28990¦28995¦29037¦29041¦29044 | 4654
29046 | Finishing Works | 4 | 51 | 28989¦28990¦28995¦29037¦29046 | 4654
29047 | Walls | 5 | 52 | 28989¦28990¦28995¦29037¦29046¦29047 | 4654
29048 | Floor | 5 | 53 | 28989¦28990¦28995¦29037¦29046¦29048 | 4654
29049 | Staircase | 5 | 54 | 28989¦28990¦28995¦29037¦29046¦29049 | 4654
29050 | Painting | 5 | 55 | 28989¦28990¦28995¦29037¦29046¦29050 | 4654
29051 | Cieling | 5 | 56 | 28989¦28990¦28995¦29037¦29046¦29051 | 4654
29052 | Services | 4 | 57 | 28989¦28990¦28995¦29037¦29052 | 4654
29053 | Electrical | 5 | 58 | 28989¦28990¦28995¦29037¦29052¦29053 | 4654
29054 | Plumbing | 5 | 59 | 28989¦28990¦28995¦29037¦29052¦29054 | 4654
29055 | Mechanical | 5 | 60 | 28989¦28990¦28995¦29037¦29052¦29055 | 4654
29056 | Fire Netwrok | 5 | 61 | 28989¦28990¦28995¦29037¦29052¦29056 | 4654
29057 | Lift Works | 5 | 62 | 28989¦28990¦28995¦29037¦29052¦29057 | 4654
28996 | Comissioning Phase | 2 | 63 | 28989¦28990¦28996 | 4654
29058 | Punchlisting / Snags | 3 | 64 | 28989¦28990¦28996¦29058 | 4654
29059 | Pre-Comissioning | 3 | 65 | 28989¦28990¦28996¦29059 | 4654
29060 | Comissioning | 3 | 66 | 28989¦28990¦28996¦29060 | 4654
28997 | Project Close Out | 2 | 67 | 28989¦28990¦28997 | 4654
29061 | Final Documentation | 3 | 68 | 28989¦28990¦28997¦29061 | 4654
29062 | Demoblization | 3 | 69 | 28989¦28990¦28997¦29062 | 4654

## R-Cal
Project Name
Project Resource Sheet
Activity ID | Activity Name | Unit | BOQ | Duration (Days) | Per Day HRs. | Total HRs. | Labor | [8 empty] | Non-Labor |  |  | Material
Office Building Works | [6 empty] | Project Eng. | Planning Eng. | Quality Eng | HSE Eng. | Design Eng. | Procurement Eng | Surveyor | Helper | Labor | Total Station | Grader | Excavator | Cement | Sand | Crush | Tile | Admixture
Project Start / Initiation Phase
Letter of Award
A1000 | Letter Of Award | Job | 1 | 6 | 8 | 48
Kick of Meeting
A1010 | Kick of Meeting | Job | 1 | 6 | 8 | 48
Mobilization Phase
Labor Resources
A1190 | Mobilization of Management Team | Job | 1 | 6 | 8 | 48
A1200 | Mobilization of Design Team | Job | 1 | 6 | 8 | 48
A1210 | Mobilization of Civil Team | Job | 1 | 5 | 8 | 40
A1220 | Mobilization of Painting Team | Job | 1 | 6 | 8 | 48
A1240 | Mobilization of Ceiling Team | Job | 1 | 6 | 8 | 48
A1250 | Mobilization of Electrical Team | Job | 1 | 6 | 8 | 48
A1260 | Mobilization of Plumbing Team | Job | 1 | 6 | 8 | 48
A1270 | Mobilization of Mechanical Team | Job | 1 | 6 | 8 | 48
A1280 | Mobilization of Fire Network Team | Job | 1 | 6 | 8 | 48
A1290 | Mobilization of Lift Works Team | Job | 1 | 6 | 8 | 48
Non-Labor Resources
A1300 | Mobilization of Equipment | Job | 1 | 6 | 8 | 48
A1310 | Mobilization of Fire Network Tools & Machinery | Job | 1 | 6 | 8 | 48
A1320 | Mobilization of Lift Tools | Job | 1 | 6 | 8 | 48
Documents Submission Phase
Preparation & Submission
A1330 | Execution Plan | Job | 1 | 6 | 8 | 48 | 5 | 6
A1340 | Project Quality Plan | Job | 1 | 6 | 8 | 48
A1350 | HSE Plan | Job | 1 | 5 | 8 | 40
Approval
A1360 | Execution Plan | Job | 1 | 6 | 8 | 48 |  |  |  |  | 65
A1380 | HSE Plan | Job | 1 | 6 | 8 | 48
A1370 | Project Quality Plan | Job | 1 | 6 | 8 | 48
Engineering & Design Phase
Conceptual Design
Preparation & Submission
A1390 | Concept Plan | Job | 1 | 4 | 8 | 32 |  |  |  |  | 128
A1400 | General Layout | Job | 1
Approval
A1410 | Concept Plan | Job | 1 | 6 | 8 | 48
A1420 | General Layout | Job | 1 | 6 | 8 | 48
Detailed Design
Sub-Structure
Preparation & Submission
A1430 | IFC for Base Foundation | Job | 1 | 6 | 8 | 48
A1440 | IFC for Raft Foundation | Job | 1 | 6 | 8 | 48
Approval
A1450 | IFC Drawings for Base Foundation | Job | 1 | 6 | 8 | 48
A1460 | IFC for Raft Foundation | Job | 1 | 6 | 8 | 48
Super Structure
Preparation & Submission
A1470 | IFC for Columns | Job | 1 | 6 | 8 | 48
A1480 | IFC for Beams | Job | 1 | 6 | 8 | 48
A1490 | IFC for Slab | Job | 1 | 6 | 8 | 48
Approval
A1500 | IFC for Columns | Job | 1 | 6 | 8 | 48
A1510 | IFC for Beams | Job | 1 | 6 | 8 | 48
A1520 | IFC for Slab | Job | 1 | 6 | 8 | 48
Electrical
Preparation & Submission
A1540 | IFC for Electrical | Job | 1 | 6 | 8 | 48
Approval
A1550 | IFC for Electrical | Job | 1 | 6 | 8 | 48
Mechanical Drawings
Preparation & Submission
A1530 | IFC for Mechanical | Job | 1 | 6 | 8 | 48
Approval
A1560 | IFC for Mechanical | Job | 1 | 6 | 8 | 48
Plumbing Drawings
Preparation & Submission
A1570 | IFC for Plumbing | Job | 1
Approval
A1580 | IFC for Plumbing | Job | 1
Fire Network Drawings
Preparation & Submission
A1590 | IFC for Fire Network | Job | 1
Approval
A1600 | IFC for Fire Network | Job | 1
Procurement Phase
Local Purchase
A1610 | Bulk Material | Job | 1
Foreign Procurement
A1620 | Chiller | Job | 1
Long lead Items
A1630 | HVAC Material | Job | 1
Construction Phase
Civil Works
Sub-Structure
Excavation
A1640 | Layout & Marking | Job | 1 | 1 | 8 | 8 | [6 empty] | 8 | 8 |  | 8 |  |  | 4
A1650 | Excavation | CUM | 400 | 8.1967 | 8 | 65.5738 | [11 empty] | 65.5738
Foundation
A1660 | Leveling & Dressing & Compaction | LM | 200 | 0 | 8 | 0 | [11 empty] | #REF!
A1670 | PCC / Lean Concrete | LM | 230 | 0 | 8 | 0
A1680 | Steel fixing | TON | 30 | 0 | 8 | 0
A1690 | Formwork installation | SQM | 400 | 0 | 8 | 0
A1700 | Pouring Concrete | CUM | 400 | 0 | 8 | 0
A1710 | Formwork Removal | SQM | 360 | 0 | 8 | 0
A1720 | Curing | Job | 1 | 0 | 8 | 0
A1730 | Bitumen Coating | SQM | 300 | 0 | 8 | 0
Super Structure
Columns & Beams
A1740 | Steel fixing | TON | 25 | 0 | 8 | 0
A1750 | Formwork installation | SQM | 200 | 0 | 8 | 0
A1760 | Pouring Concrete | CUM | 200 | 0 | 8 | 0
A1770 | Formwork Removal | SQM | 190 | 0 | 8 | 0
A1780 | Curing | Job | 1 | 0 | 8 | 0
Slab Works
A1790 | Formwork installation | SQM | 25 | 0 | 8 | 0
A1800 | Steel fixing | TON | 200 | 0 | 8 | 0
A1810 | Pouring Concrete | CUM | 200 | 0 | 8 | 0
A1820 | Formwork Removal | SQM | 190 | 0 | 8 | 0
A1830 | Curing | Job | 1 | 0 | 8 | 0
Masonry Works
A1840 | Masonry Works | SQM | 190 | 0 | 8 | 0
Finishing Works
Walls
A1850 | Plaster Inner | SQM | 190 | 0 | 8 | 0
A1860 | Plaster Outer | SQM | 190 | 0 | 8 | 0
Floor
A1870 | Screeding | SQM | 190 | 0 | 8 | 0
A1880 | Tiling Work | SQM | 190 | 0 | 8 | 0
Staircase
A1890 | Formwork | SQM | 25 | 0 | 8 | 0
A1900 | Steel fixing | TON | 200 | 0 | 8 | 0
A1910 | Pouring Concrete | CUM | 200 | 0 | 8 | 0
A1920 | Formwork Removal | SQM | 190 | 0 | 8 | 0
A1930 | Tiling / Marble works | Job | 1 | 0 | 8 | 0
Painting
A1940 | Painting Inner | SQM | 190 | 0 | 8 | 0
A1950 | Painting Outer | SQM | 190 | 0 | 8 | 0
Ceiling
A1960 | Ceiling Work | SQM | 200 | 0 | 8 | 0
Services
Electrical
A1970 | Fabrication & Installation of Cable Trays/Ducts | LM | 300 | 0 | 8 | 0
A1980 | Laying of cables | LM | 400 | 0 | 8 | 0
A1990 | Installation of DB's & Fixtures | NOs | 200 | 0 | 8 | 0
A2000 | Gladding & Termination / Connections | Job | 230 | 0 | 8 | 0
Plumbing
A2030 | Fixtures installations | LM | 300 | 0 | 8 | 0
A2020 | Installation / Erection of Piping | LM | 200 | 0 | 8 | 0
A2010 | Fabrication & Installation & Insulation of Ducts | LM | 230 | 0 | 8 | 0
Mechanical
A2040 | Fabrication railing for staircase | TON | 40 | 0 | 8 | 0
A2060 | Painting Works | SQM | 200 | 0 | 8 | 0
A2050 | Erection of Railing | TON | 40 | 0 | 8 | 0
Fire Network
A2070 | Fabrication and installation of FW piping | LM | 200 | 0 | 8 | 0
A2080 | Installation of Firehouse | NOs | 13 | 0 | 8 | 0
A2090 | Installation of High pressure Pump | NOs | 14 | 0 | 8 | 0
Lift Works
A2120 | Interior finishing | SQM | 40 | 0 | 8 | 0
A2110 | Installation of Motor | NOs | 5 | 0 | 8 | 0
A2100 | Installation of frame & Rail & Counter weight | NOs | 4 | 0 | 8 | 0
A2130 | Connections | Job | 12 | 0 | 8 | 0
Commissioning Phase
Punch listing / Snags
A2150 | Pun listing for Basement | Job | 1 | 0 | 8 | 0
A2140 | Pun listing for Ground Floor | Job | 1 | 0 | 8 | 0
Pre-Commissioning
A2170 | Closing of A type Punch Points | Job | 1 | 0 | 8 | 0
A2160 | Testing of Services | Job | 1 | 0 | 8 | 0
Commissioning
A2190 | Commissioning of Basement | Job | 1 | 0 | 8 | 0
A2180 | Commissioning of GF | Job | 1 | 0 | 8 | 0
Project Close Out
Final Documentation
A2210 | Submission of Final Dossier | Job | 1 | 0 | 8 | 0
A2200 | Submission of Design Package (As-Built) | Job | 1 | 0 | 8 | 0
Demobilization
A2220 | Demobilization | Job | 1 | 0 | 8 | 0
Note on L38: Windows User:

## Cal_Data_Day (hidden)
clndr_id | Cal_day | Cal_day_Hours
6773 | 45172 | 8
6773 | 45173 | 8
6773 | 45174 | 8
6773 | 45175 | 8
6773 | 45176 | 8
6773 | 45177
6773 | 45178
6773 | 45179 | 8
6773 | 45180 | 8
6773 | 45181 | 8
6773 | 45182 | 8
6773 | 45183 | 8
6773 | 45184
6773 | 45185
6773 | 45186 | 8
6773 | 45187 | 8
6773 | 45188 | 8
6773 | 45189 | 8
6773 | 45190 | 8
6773 | 45191
6773 | 45192
6773 | 45193 | 8
6773 | 45194 | 8
6773 | 45195 | 8
6773 | 45196 | 8
6773 | 45197 | 8
6773 | 45198
6773 | 45199
6773 | 45200 | 8
6773 | 45201 | 8
6773 | 45202 | 8
6773 | 45203 | 8
6773 | 45204 | 8
6773 | 45205
6773 | 45206
6773 | 45207 | 8
6773 | 45208 | 8
6773 | 45209 | 8
6773 | 45210 | 8
6773 | 45211 | 8
6773 | 45212
6773 | 45213
6773 | 45214 | 8
6773 | 45215 | 8
6773 | 45216 | 8
6773 | 45217 | 8
6773 | 45218 | 8
6773 | 45219
6773 | 45220
6773 | 45221 | 8
6773 | 45222 | 8
6773 | 45223 | 8
6773 | 45224 | 8
6773 | 45225 | 8
6773 | 45226
6773 | 45227
6773 | 45228 | 8
6773 | 45229 | 8
6773 | 45230 | 8
6773 | 45231 | 8
6773 | 45232 | 8
6773 | 45233
6773 | 45234
6773 | 45235 | 8
6773 | 45236 | 8
6773 | 45237 | 8
6773 | 45238 | 8
6773 | 45239 | 8
6773 | 45240
6773 | 45241
6773 | 45242 | 8
6773 | 45243 | 8
6773 | 45244 | 8
6773 | 45245 | 8
6773 | 45246 | 8
6773 | 45247
6773 | 45248
6773 | 45249 | 8
6773 | 45250 | 8
6773 | 45251 | 8
6773 | 45252 | 8
6773 | 45253 | 8
6773 | 45254
6773 | 45255
6773 | 45256 | 8
6773 | 45257 | 8
6773 | 45258 | 8
6773 | 45259 | 8
6773 | 45260 | 8
6773 | 45261
6773 | 45262
6773 | 45263 | 4
6773 | 45264 | 8
6773 | 45265 | 8
6773 | 45266 | 8
6773 | 45267 | 8
6773 | 45268
6773 | 45269
6773 | 45270 | 8
6773 | 45271 | 8
6773 | 45272 | 8
6773 | 45273 | 8
6773 | 45274 | 8
6773 | 45275
6773 | 45276
6773 | 45277 | 8
6773 | 45278 | 8
6773 | 45279 | 8
6773 | 45280 | 8
6773 | 45281 | 8
6773 | 45282
6773 | 45283
6773 | 45284 | 8
6773 | 45285 | 8
6773 | 45286 | 8
6773 | 45287 | 8
6773 | 45288 | 8
6773 | 45289
6773 | 45290
6773 | 45291 | 8
6773 | 45292 | 8
6773 | 45293 | 8
6773 | 45294 | 8
6773 | 45295 | 8
6773 | 45296
6773 | 45297
6773 | 45298 | 8
6773 | 45299 | 8
6773 | 45300 | 8
6773 | 45301 | 8
6773 | 45302 | 8
6773 | 45303
6773 | 45304
6773 | 45305 | 8
6773 | 45306 | 8
6773 | 45307 | 8
6773 | 45308 | 8
6773 | 45309 | 8
6773 | 45310
6773 | 45311
6773 | 45312 | 8
6773 | 45313 | 8
6773 | 45314 | 8
6773 | 45315 | 8
6773 | 45316 | 8
6773 | 45317
6773 | 45318
6773 | 45319 | 8
6773 | 45320 | 8
6773 | 45321 | 8
6773 | 45322 | 8
6773 | 45323 | 8
6773 | 45324
6773 | 45325
6773 | 45326 | 8
6773 | 45327 | 8
6773 | 45328 | 8
6773 | 45329 | 8
6773 | 45330 | 8
6773 | 45331
6773 | 45332
6773 | 45333 | 8
6773 | 45334 | 8
6773 | 45335 | 8
6773 | 45336 | 8
6773 | 45337 | 8
6773 | 45338
6773 | 45339
6773 | 45340 | 8
6773 | 45341 | 8
6773 | 45342 | 8
6773 | 45343 | 8
6773 | 45344 | 8
6773 | 45345
6773 | 45346
6773 | 45347 | 8
6773 | 45348 | 8
6773 | 45349 | 8
6773 | 45350 | 8
6773 | 45351 | 8
6773 | 45352
6773 | 45353
6773 | 45354 | 8
6773 | 45355 | 8
6773 | 45356 | 8
6773 | 45357 | 8
6773 | 45358 | 8
6773 | 45359
6773 | 45360
6773 | 45361 | 8
6773 | 45362 | 8
6773 | 45363 | 8
6773 | 45364 | 8
6773 | 45365 | 8
6773 | 45366
6773 | 45367
6773 | 45368 | 8
6773 | 45369 | 8
6773 | 45370 | 8
6773 | 45371 | 8
6773 | 45372 | 8
6773 | 45373
6773 | 45374
6773 | 45375 | 8
6773 | 45376 | 8
6773 | 45377 | 8
6773 | 45378 | 8
6773 | 45379 | 8
6773 | 45380
6773 | 45381
6773 | 45382 | 8
6773 | 45383 | 8
6773 | 45384 | 8
6773 | 45385 | 8
6773 | 45386 | 8
6773 | 45387
6773 | 45388
6773 | 45389 | 8
6773 | 45390 | 8

## Cal_Data (hidden)
clndr_id | type | Date | Hours | Key
6773 | DaysOfWeek | 1 | 8 | A6773.1
6773 | DaysOfWeek | 2 | 8 | A6773.2
6773 | DaysOfWeek | 3 | 8 | A6773.3
6773 | DaysOfWeek | 4 | 8 | A6773.4
6773 | DaysOfWeek | 5 | 8 | A6773.5
6773 | DaysOfWeek | 6 |  | A6773.6
6773 | DaysOfWeek | 7 |  | A6773.7
6773 | Exceptions | 45172 | 8 | A6773.45172
6773 | Exceptions | 45263 | 4 | A6773.45263

## Table_Summary (hidden)
C:\Users\Planning-P6\Desktop\BL-001.xer
Tables | Row | Nr record
CURRTYPE | 2 | 18
FINTMPL | 22 | 1
OBS | 25 | 1
UDFTYPE | 28 | 1
PROJECT | 31 | 1
CALENDAR | 34 | 1
SCHEDOPTIONS | 37 | 1
PROJWBS | 40 | 69
ACTVTYPE | 111 | 2
TASK | 115 | 121
ACTVCODE | 238 | 4
TASKPRED | 244 | 138
TASKPROC | 384 | 3
UDFVALUE | 389 | 121

## UDFVALUE (hidden)
udf_type_id | fk_id | proj_id | udf_date | udf_number | udf_text | udf_code_id
987 | 120161 | 4654 |  | 0
987 | 120162 | 4654 |  | 8
987 | 120228 | 4654 |  | 0
987 | 120229 | 4654 |  | 0
987 | 120230 | 4654 |  | 0
987 | 120241 | 4654 |  | 0
987 | 120242 | 4654 |  | 0
987 | 120243 | 4654 |  | 0
987 | 120244 | 4654 |  | 0
987 | 120279 | 4654 |  | 0
987 | 120280 | 4654 |  | 0
987 | 120281 | 4654 |  | 0
987 | 120282 | 4654 |  | 0
987 | 120283 | 4654 |  | 0
987 | 120284 | 4654 |  | 0
987 | 120285 | 4654 |  | 0
987 | 120286 | 4654 |  | 0
987 | 120287 | 4654 |  | 0
987 | 120288 | 4654 |  | 8
987 | 120289 | 4654 |  | 8
987 | 120290 | 4654 |  | 8
987 | 120291 | 4654 |  | 8
987 | 120293 | 4654 |  | 8
987 | 120294 | 4654 |  | 8
987 | 120295 | 4654 |  | 8
987 | 120296 | 4654 |  | 8
987 | 120297 | 4654 |  | 8
987 | 120298 | 4654 |  | 8
987 | 120299 | 4654 |  | 8
987 | 120300 | 4654 |  | 8
987 | 120301 | 4654 |  | 8
987 | 120302 | 4654 |  | 8
987 | 120303 | 4654 |  | 8
987 | 120304 | 4654 |  | 8
987 | 120305 | 4654 |  | 8
987 | 120306 | 4654 |  | 8
987 | 120307 | 4654 |  | 8
987 | 120308 | 4654 |  | 8
987 | 120309 | 4654 |  | 8
987 | 120310 | 4654 |  | 8
987 | 120311 | 4654 |  | 8
987 | 120312 | 4654 |  | 8
987 | 120313 | 4654 |  | 8
987 | 120314 | 4654 |  | 8
987 | 120315 | 4654 |  | 8
987 | 120316 | 4654 |  | 8
987 | 120317 | 4654 |  | 8
987 | 120318 | 4654 |  | 8
987 | 120319 | 4654 |  | 8
987 | 120320 | 4654 |  | 8
987 | 120321 | 4654 |  | 8
987 | 120322 | 4654 |  | 8
987 | 120323 | 4654 |  | 8
987 | 120324 | 4654 |  | 8
987 | 120325 | 4654 |  | 8
987 | 120326 | 4654 |  | 8
987 | 120327 | 4654 |  | 8
987 | 120328 | 4654 |  | 8
987 | 120329 | 4654 |  | 8
987 | 120330 | 4654 |  | 8
987 | 120331 | 4654 |  | 8
987 | 120332 | 4654 |  | 8
987 | 120333 | 4654 |  | 8
987 | 120334 | 4654 |  | 8
987 | 120335 | 4654 |  | 8
987 | 120336 | 4654 |  | 8
987 | 120337 | 4654 |  | 8
987 | 120338 | 4654 |  | 8
987 | 120339 | 4654 |  | 8
987 | 120340 | 4654 |  | 8
987 | 120341 | 4654 |  | 8
987 | 120342 | 4654 |  | 8
987 | 120343 | 4654 |  | 8
987 | 120344 | 4654 |  | 8
987 | 120345 | 4654 |  | 8
987 | 120346 | 4654 |  | 8
987 | 120347 | 4654 |  | 8
987 | 120349 | 4654 |  | 8
987 | 120350 | 4654 |  | 8
987 | 120351 | 4654 |  | 8
987 | 120352 | 4654 |  | 8
987 | 120353 | 4654 |  | 8
987 | 120354 | 4654 |  | 8
987 | 120355 | 4654 |  | 8
987 | 120356 | 4654 |  | 8
987 | 120357 | 4654 |  | 8
987 | 120358 | 4654 |  | 8
987 | 120359 | 4654 |  | 8
987 | 120360 | 4654 |  | 8
987 | 120361 | 4654 |  | 8
987 | 120362 | 4654 |  | 8
987 | 120363 | 4654 |  | 8
987 | 120364 | 4654 |  | 8
987 | 120365 | 4654 |  | 8
987 | 120366 | 4654 |  | 8
987 | 124932 | 4654 |  | 8
987 | 124933 | 4654 |  | 8
987 | 124934 | 4654 |  | 8
987 | 124935 | 4654 |  | 8
987 | 124936 | 4654 |  | 8
987 | 124937 | 4654 |  | 8
987 | 124938 | 4654 |  | 8
987 | 124940 | 4654 |  | 8
987 | 124941 | 4654 |  | 8
987 | 124942 | 4654 |  | 8
987 | 124944 | 4654 |  | 8
987 | 124945 | 4654 |  | 8
987 | 124946 | 4654 |  | 8
987 | 124947 | 4654 |  | 8
987 | 124948 | 4654 |  | 8
987 | 124949 | 4654 |  | 8
987 | 124950 | 4654 |  | 8
987 | 124951 | 4654 |  | 8
987 | 124952 | 4654 |  | 8
987 | 124954 | 4654 |  | 8
987 | 124955 | 4654 |  | 8
987 | 124956 | 4654 |  | 8
987 | 124957 | 4654 |  | 8
987 | 124958 | 4654 |  | 8
987 | 124959 | 4654 |  | 8
987 | 124960 | 4654 |  | 8

## TASKPROC (hidden)
proc_id | task_id | proj_id | seq_num | proc_name | complete_flag | proc_wt | complete_pct | proc_descr
32659 | 124936 | 4654 | 0 | Fabrication | Y | 50 | 100
32660 | 124936 | 4654 | 100 | Installation | N | 25 | 0
32661 | 124936 | 4654 | 200 | Insulation | N | 25 | 0

## TASKPRED (hidden)
task_pred_id | task_id | pred_task_id | proj_id | pred_proj_id | pred_type | lag_hr_cnt | comments | float_path | aref | arls
96773 | 120162 | 120161 | 4654 | 4654 | PR_SS | 16 |  |  | 2023-09-04 17:00 | 2024-04-01 08:00
96774 | 120228 | 120161 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-03 08:00 | 2024-04-08 17:00
96776 | 120229 | 120288 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-03 08:00 | 2024-04-03 08:00
96777 | 120230 | 120308 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-21 08:00 | 2024-04-03 08:00
96778 | 120241 | 120330 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-27 17:00 | 2024-04-08 17:00
96779 | 120242 | 120333 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2024-04-08 17:00
96780 | 120243 | 124951 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-03 08:00 | 2024-04-03 08:00
96781 | 120244 | 124958 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-03 08:00 | 2024-04-03 08:00
96782 | 120279 | 120298 | 4654 | 4654 | PR_FF | 0 |  |  | 2024-04-07 17:00 | 2024-04-08 17:00
96783 | 120279 | 120301 | 4654 | 4654 | PR_FF | 0 |  |  | 2024-04-07 17:00 | 2024-04-08 17:00
96784 | 120280 | 120325 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-21 17:00 | 2024-04-08 17:00
96785 | 120280 | 120329 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-15 17:00 | 2024-04-08 17:00
96786 | 120281 | 120332 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-27 17:00 | 2024-04-08 17:00
96787 | 120281 | 120331 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-27 17:00 | 2024-04-08 17:00
96788 | 120282 | 124950 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96789 | 120282 | 120365 | 4654 | 4654 | PR_FF | 0 |  |  | 2024-04-08 17:00 | 2024-04-08 17:00
96790 | 120283 | 124956 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96791 | 120283 | 124957 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96801 | 120284 | 124960 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96803 | 120285 | 120162 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-10 17:00 | 2024-04-08 17:00
96805 | 120286 | 120329 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-15 17:00 | 2024-04-08 17:00
96806 | 120286 | 120324 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-11-09 17:00 | 2024-04-08 17:00
96807 | 120287 | 124950 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96808 | 120287 | 124946 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96809 | 120287 | 124942 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96810 | 120287 | 124938 | 4654 | 4654 | PR_FF | 0 |  |  | 2023-09-06 17:00 | 2024-04-08 17:00
96811 | 120287 | 124935 | 4654 | 4654 | PR_FF | 0 |  |  | 2024-04-07 17:00 | 2024-04-08 17:00
96812 | 120288 | 120161 | 4654 | 4654 | PR_SS | 0 |  |  | 2023-09-03 08:00 | 2023-09-03 08:00
96813 | 120289 | 120288 | 4654 | 4654 | PR_SS | 16 |  |  | 2023-09-04 17:00 | 2023-09-07 08:00
96814 | 120290 | 120289 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-10 17:00 | 2023-10-15 08:00
96815 | 120291 | 120290 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-14 17:00 | 2024-02-28 08:00
96816 | 120293 | 120291 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-04 17:00 | 2024-03-05 08:00
96817 | 120294 | 120293 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-10 17:00 | 2024-03-11 08:00
96818 | 120295 | 120294 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-14 17:00 | 2024-03-18 08:00
96819 | 120296 | 120295 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-20 17:00 | 2024-03-24 08:00
96820 | 120297 | 120296 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-26 17:00 | 2024-03-28 08:00
96821 | 120298 | 120297 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-04-01 17:00 | 2024-04-03 08:00
96822 | 120299 | 120288 | 4654 | 4654 | PR_FS | 24 |  |  | 2023-09-11 17:00 | 2024-03-31 08:00
96823 | 120300 | 120297 | 4654 | 4654 | PR_SS | 0 |  |  | 2024-03-27 08:00 | 2024-03-28 08:00
96824 | 120301 | 120298 | 4654 | 4654 | PR_SS | 0 |  |  | 2024-04-02 08:00 | 2024-03-28 08:00
96825 | 120302 | 120288 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-06 17:00 | 2023-09-07 08:00
96826 | 120303 | 120302 | 4654 | 4654 | PR_SS | 16 |  |  | 2023-09-10 17:00 | 2023-09-03 08:00
96827 | 120303 | 120288 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-06 17:00 | 2023-09-11 08:00
96828 | 120304 | 120302 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-12 17:00 | 2024-04-03 08:00
96829 | 120304 | 120303 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-14 17:00 | 2024-04-03 08:00
96830 | 120305 | 120302 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-12 17:00 | 2024-04-03 08:00
96831 | 120306 | 120303 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-14 17:00 | 2023-09-17 08:00
96832 | 120307 | 120303 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-14 17:00 | 2024-04-03 08:00
96833 | 120308 | 120289 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-10 17:00 | 2023-09-21 08:00
96834 | 120308 | 120306 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-20 17:00 | 2023-09-21 08:00
96835 | 120309 | 120308 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-26 17:00 | 2023-09-27 08:00
96836 | 120310 | 120308 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-26 17:00 | 2023-10-03 08:00
96837 | 120311 | 120309 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-02 17:00 | 2023-10-03 08:00
96838 | 120312 | 120310 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-02 17:00 | 2023-10-09 08:00
96839 | 120312 | 120311 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-08 17:00 | 2023-10-09 08:00
96840 | 120313 | 120312 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-12 17:00 | 2024-02-28 08:00
96841 | 120314 | 120312 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-12 17:00 | 2023-10-15 08:00
96842 | 120315 | 120313 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-18 17:00 | 2024-03-05 08:00
96843 | 120316 | 120312 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-12 17:00 | 2023-11-30 08:00
96844 | 120317 | 120316 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-18 17:00 | 2023-12-06 08:00
96845 | 120318 | 120317 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2024-01-03 08:00
96846 | 120319 | 120316 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-18 17:00 | 2023-12-12 08:00
96847 | 120320 | 120317 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2023-12-12 08:00
96848 | 120321 | 120318 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-30 17:00 | 2024-01-09 08:00
96849 | 120323 | 120318 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-30 17:00 | 2024-02-18 08:00
96850 | 120324 | 120323 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2024-02-22 08:00
96851 | 120322 | 120324 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2024-02-28 08:00
96852 | 120325 | 120322 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-15 17:00 | 2024-03-05 08:00
96853 | 120326 | 120321 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2024-02-28 08:00
96854 | 120327 | 120326 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2024-03-05 08:00
96855 | 120328 | 120321 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2024-02-28 08:00
96856 | 120329 | 120328 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2024-03-05 08:00
96857 | 120330 | 120329 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-15 17:00 | 2024-03-11 08:00
96858 | 120330 | 120327 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-15 17:00 | 2024-03-11 08:00
96859 | 120330 | 120325 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-21 17:00 | 2024-03-11 08:00
96860 | 120330 | 120324 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2024-03-11 08:00
96861 | 120330 | 120321 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2024-03-11 08:00
96862 | 120330 | 120320 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-30 17:00 | 2024-03-11 08:00
96863 | 120330 | 120319 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2024-03-11 08:00
96864 | 120330 | 120315 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2024-03-11 08:00
96865 | 120330 | 120314 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-18 17:00 | 2024-03-11 08:00
96866 | 120331 | 120325 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-21 17:00 | 2024-04-03 08:00
96867 | 120332 | 120325 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-21 17:00 | 2024-04-03 08:00
96868 | 120333 | 120290 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-09-14 17:00 | 2023-10-19 08:00
96869 | 120333 | 120314 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-18 17:00 | 2023-10-19 08:00
96870 | 120333 | 120311 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-08 17:00 | 2023-10-19 08:00
96871 | 120334 | 120333 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2023-10-25 08:00
96872 | 120335 | 120334 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-30 17:00 | 2023-10-31 08:00
96873 | 120336 | 120335 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2023-11-06 08:00
96874 | 120337 | 120336 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2023-11-12 08:00
96875 | 120338 | 120337 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-15 17:00 | 2023-11-16 08:00
96876 | 120339 | 120338 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-21 17:00 | 2023-11-22 08:00
96877 | 120340 | 120339 | 4654 | 4654 | PR_FS | 16 |  |  | 2023-11-29 17:00 | 2023-11-28 08:00
96878 | 120341 | 120340 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-12-05 17:00 | 2023-12-06 08:00
96879 | 120342 | 120341 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-12-11 17:00 | 2023-12-12 08:00
96880 | 120343 | 120342 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-12-17 17:00 | 2023-12-18 08:00
96881 | 120344 | 120343 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-12-21 17:00 | 2023-12-24 08:00
96882 | 120345 | 120344 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-12-27 17:00 | 2023-12-28 08:00
96883 | 120346 | 120345 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-02 17:00 | 2024-01-03 08:00
96884 | 120347 | 120346 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-08 17:00 | 2024-01-09 08:00
96885 | 120343 | 120319 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-24 17:00 | 2023-12-18 08:00
96886 | 120343 | 120320 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-10-30 17:00 | 2023-12-18 08:00
96887 | 120349 | 120347 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-14 17:00 | 2024-01-15 08:00
96888 | 120350 | 120349 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-18 17:00 | 2024-01-21 08:00
96889 | 120351 | 120350 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-24 17:00 | 2024-01-25 08:00
96890 | 120352 | 120351 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-30 17:00 | 2024-01-31 08:00
96891 | 120353 | 120352 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-05 17:00 | 2024-02-06 08:00
96892 | 120349 | 120321 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-05 17:00 | 2024-01-15 08:00
96893 | 120354 | 120353 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-11 17:00 | 2024-03-11 08:00
96894 | 120355 | 120354 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-15 17:00 | 2024-03-24 08:00
96895 | 120356 | 120355 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-27 17:00 | 2024-03-28 08:00
96896 | 120357 | 120353 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-11 17:00 | 2024-02-12 08:00
96897 | 120358 | 120357 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-15 17:00 | 2024-02-18 08:00
96898 | 120360 | 120350 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-24 17:00 | 2024-04-03 08:00
96899 | 120361 | 120351 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-01-30 17:00 | 2024-04-03 08:00
96900 | 120362 | 120352 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-05 17:00 | 2024-04-03 08:00
96901 | 120363 | 120358 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-21 17:00 | 2024-02-22 08:00
96902 | 120364 | 120355 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-27 17:00 | 2024-03-28 08:00
96903 | 120364 | 120358 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-21 17:00 | 2024-03-28 08:00
96904 | 120365 | 120356 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-04-02 17:00 | 2024-04-03 08:00
96905 | 120366 | 120364 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-04-02 17:00 | 2024-04-03 08:00
96906 | 124932 | 120324 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-09 17:00 | 2024-03-17 08:00
96907 | 124932 | 120330 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-27 17:00 | 2024-03-17 08:00
96908 | 124932 | 120354 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-15 17:00 | 2024-03-17 08:00
96909 | 120355 | 124932 | 4654 | 4654 | PR_SS | 40 |  |  | 2024-03-21 17:00 | 2024-03-11 08:00
96910 | 124933 | 124932 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-20 17:00 | 2024-03-24 08:00
96911 | 124934 | 124933 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-26 17:00 | 2024-03-28 08:00
96912 | 124935 | 124934 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-04-01 17:00 | 2024-04-03 08:00
96913 | 124935 | 124933 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-26 17:00 | 2024-04-03 08:00
96915 | 124936 | 120327 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-15 17:00 | 2024-04-03 08:00
96916 | 124936 | 120330 | 4654 | 4654 | PR_FS | 0 |  |  | 2023-11-27 17:00 | 2024-04-03 08:00
96917 | 124936 | 120295 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-20 17:00 | 2024-04-03 08:00
96918 | 124932 | 120294 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-14 17:00 | 2024-03-17 08:00
96919 | 120366 | 120293 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-10 17:00 | 2024-04-03 08:00
96920 | 120364 | 120291 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-03-04 17:00 | 2024-03-28 08:00
96921 | 120291 | 120363 | 4654 | 4654 | PR_FS | 0 |  |  | 2024-02-27 17:00 | 2024-02-28 08:00
103708 | 120359 | 120349 | 4654 | 4654 | PR_FF | 8 |  |  | 2024-01-16 08:00 | 2024-04-07 08:00
103709 | 120360 | 120359 | 4654 | 4654 | PR_FF | 8 |  |  | 2024-01-17 08:00 | 2024-04-08 08:00

## ACTVCODE (hidden)
actv_code_id | parent_actv_code_id | actv_code_type_id | actv_code_name | short_name | seq_num | color | total_assignments
7731 |  | 1645 | Civil Works | CIVIL | 0 | 80FF00
7737 |  | 1646 | (New Code Value) | (New) | 0 | 0000FF
7738 |  | 1646 | (New Code Value) | (New)-1 | 100 | 0000FF
7739 |  | 1646 | (New Code Value) | (New)-2 | 101 | 0000FF

## TASK (hidden)
task_id | proj_id | wbs_id | clndr_id | phys_complete_pct | rev_fdbk_flag | est_wt | lock_plan_flag | auto_compute_act_flag | complete_pct_type | task_type | duration_type | status_code | task_code | task_name | rsrc_id | total_float_hr_cnt | free_float_hr_cnt | remain_drtn_hr_cnt | act_work_qty | remain_work_qty | target_work_qty | target_drtn_hr_cnt | target_equip_qty | act_equip_qty | remain_equip_qty | cstr_date | act_start_date | act_end_date | late_start_date | late_end_date | expect_end_date | early_start_date | early_end_date | restart_date | reend_date | target_start_date | target_end_date | rem_late_start_date | rem_late_end_date | cstr_type | priority_type | suspend_date | resume_date | float_path | float_path_order | guid | tmpl_guid | cstr_date2 | cstr_type2 | driving_path_flag | act_this_per_work_qty | act_this_per_equip_qty | external_early_start_date | external_late_end_date | create_date | update_date | create_user | update_user | location_id | crt_path_num
120161 | 4654 | 28998 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1000 | Letter Of Award |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-09-03 08:00 | 2023-09-03 08:00 |  | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 |  | PT_Normal |  |  |  |  | 3aeNevLzwEG4kcyyOhCTOA |  |  |  | Y | 0 | 0 |  |  | 2023-09-03 21:30 | 2023-10-13 22:32
120162 | 4654 | 28999 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1010 | Kick of Meeting |  | 1208 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-05 08:00 | 2023-09-10 17:00 | 2023-09-05 08:00 | 2023-09-10 17:00 | 2023-09-05 08:00 | 2023-09-10 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | UA09nyLMzkS6JzqNwuCNow | 3aeNevLzwEG4kcyyOhCTOA |  |  | N | 0 | 0 |  |  | 2023-09-03 22:13 | 2023-10-13 22:32
120228 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1020 | Start of Project Start / Initiation Phase |  | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | HWr4ZmM6yUWnMmJaZXugzw |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:31 | 2023-10-13 22:32
120229 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1030 | Start of Mobilization Phase |  | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | Hfd4z99ZDUGchMSOUD1UCw |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:31 | 2023-10-13 22:32
120230 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1040 | Start of Engineering & Design Phase |  | 1144 | 1144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-21 08:00 | 2023-09-21 08:00 | 2023-09-21 08:00 | 2023-09-21 08:00 | 2023-09-21 08:00 | 2023-09-21 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | SkIHqbA2qUmoKBbTH9cmVg |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:31 | 2023-10-13 22:32
120241 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1050 | Start of Procurement Phase |  | 760 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-11-28 08:00 | 2023-11-28 08:00 | 2023-11-28 08:00 | 2023-11-28 08:00 | 2023-11-28 08:00 | 2023-11-28 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | hrnl4GHj6E+b1FVvKtDdEA |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:36 | 2023-10-13 22:32
120242 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1060 | Start of Construction Phase |  | 952 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-10-25 08:00 | 2023-10-25 08:00 | 2023-10-25 08:00 | 2023-10-25 08:00 | 2023-10-25 08:00 | 2023-10-25 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | uZiGvMXXf02bRBaRLgn6Tg |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:36 | 2023-10-13 22:32
120243 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1070 | Start of Commissioning Phase |  | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | c9W0kXT3/EC7BVA4H5I1xQ |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:36 | 2023-10-13 22:32
120244 | 4654 | 29001 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Mile | DT_FixedDrtn | TK_NotStart | A1080 | Start of Project Close Out |  | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2023-09-03 08:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | rInSUXoeME2W7xcUn56sJA |  |  |  | N | 0 | 0 |  |  | 2023-09-03 22:36 | 2023-10-13 22:32
120279 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1100 | Finish of Mobilization Phase |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 77NIs5eLi0mlNtwOZ3njew |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120280 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1110 | Finish of Engineering & Design Phase |  | 792 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-11-21 17:00 | 2023-11-21 17:00 | 2023-11-21 17:00 | 2023-11-21 17:00 | 2023-11-21 17:00 | 2023-11-21 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | AO2p7labMUSNFbY3Iodzgg |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120281 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1120 | Finish of Procurement Phase |  | 760 | 760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-11-27 17:00 | 2023-11-27 17:00 | 2023-11-27 17:00 | 2023-11-27 17:00 | 2023-11-27 17:00 | 2023-11-27 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 1/a2qSWog0GD29d+XUBtZA |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120282 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1130 | Finish of Construction Phase |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | gg4gvkhEoEa8sZloWR9VRQ |  |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120283 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1140 | Finish of Commissioning Phase |  | 1224 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | cBGOXCO7gkKP2g4Mm92U9g |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120284 | 4654 | 29002 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1150 | Finish of Project Close Out |  | 1224 | 1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2023-09-06 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | KRh3LemDPEuG58no1NvsAQ |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120285 | 4654 | 29003 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1160 | 20% Advance Payment |  | 1208 | 1208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-09-10 17:00 | 2023-09-10 17:00 | 2023-09-10 17:00 | 2023-09-10 17:00 | 2023-09-10 17:00 | 2023-09-10 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | vJks4ddpEkKV80lzcDbLrA |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120286 | 4654 | 29003 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1170 | 20% Completion of Design |  | 824 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2023-11-15 17:00 | 2023-11-15 17:00 | 2023-11-15 17:00 | 2023-11-15 17:00 | 2023-11-15 17:00 | 2023-11-15 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | hRy0PvDpgEW4hEoBlVHqDw |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120287 | 4654 | 29003 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_FinMile | DT_FixedDrtn | TK_NotStart | A1180 | 60% Completion of Construction |  | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2024-04-08 17:00 | 2024-04-08 17:00 |  | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-07 17:00 | 2024-04-08 17:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | xRgEgUq5RkykU+s5fO8gUw |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120288 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1190 | Mobilization of Management Team |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-03 08:00 | 2023-09-06 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 |  | PT_Normal |  |  |  |  | 2v9o07Hx/Uq9CyWJvobihw |  |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120289 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1200 | Mobilization of Design Team |  | 64 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-17 08:00 | 2023-09-20 17:00 |  | 2023-09-05 08:00 | 2023-09-10 17:00 | 2023-09-05 08:00 | 2023-09-10 17:00 | 2023-09-05 08:00 | 2023-09-10 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 |  | PT_Normal |  |  |  |  | wPtvLjMiNUqT05B/QMGzIA |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120290 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1210 | Mobilization of Civil Team |  | 192 | 192 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-15 08:00 | 2023-10-18 17:00 |  | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 |  | PT_Normal |  |  |  |  | nuDvQy+6zUO/Lq+POCZBpA |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120291 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1220 | Mobilization of Painting Team |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-28 08:00 | 2024-03-04 17:00 |  | 2024-02-28 08:00 | 2024-03-04 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 |  | PT_Normal |  |  |  |  | K/ce7QhsyEWbHe3gvXGwzw |  |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120293 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1240 | Mobilization of Ceiling Team |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-05 08:00 | 2024-03-10 17:00 |  | 2024-03-05 08:00 | 2024-03-10 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 |  | PT_Normal |  |  |  |  | omDJPDxOfkmrjIMcbfLhVg |  |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120294 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1250 | Mobilization of Electrical Team |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-11 08:00 | 2024-03-14 17:00 |  | 2024-03-11 08:00 | 2024-03-14 17:00 | 2024-03-11 08:00 | 2024-03-14 17:00 | 2024-03-11 08:00 | 2024-03-14 17:00 | 2024-03-11 08:00 | 2024-03-14 17:00 |  | PT_Normal |  |  |  |  | xIfWuhRFs0eDMfUYyIrF6w |  |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120295 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1260 | Mobilization of Plumbing Team |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-18 08:00 | 2024-03-21 17:00 |  | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-18 08:00 | 2024-03-21 17:00 |  | PT_Normal |  |  |  |  | SznJWGBD4Uiujw1dXZAIkg |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120296 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1270 | Mobilization of Mechanical Team |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-24 08:00 | 2024-03-27 17:00 |  | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-24 08:00 | 2024-03-27 17:00 |  | PT_Normal |  |  |  |  | eYC6ukmaNkGgcr5Y2TnkZQ |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120297 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1280 | Mobilization of Fire Network Team |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-28 08:00 | 2024-04-02 17:00 |  | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 |  | PT_Normal |  |  |  |  | #NAME? |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120298 | 4654 | 29005 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1290 | Mobilization of Lift Works Team |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | QO1G67szqUixtFQMbr95Gg |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120299 | 4654 | 29006 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1300 | Mobilization of Equipment |  | 1168 | 1168 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-12 08:00 | 2023-09-17 17:00 | 2023-09-12 08:00 | 2023-09-17 17:00 | 2023-09-12 08:00 | 2023-09-17 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | U3K/AXWSoU6+/9hZ8w35ug |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120300 | 4654 | 29006 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1310 | Mobilization of Fire Network Tools & Machinery |  | 40 | 40 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | mxIQeOFQ20aeyVTPttRcoQ |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120301 | 4654 | 29006 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1320 | Mobilization of Lift Tools |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | EKfSV3fAI0CDH0P5zKtO8A |  |  |  | N | 0 | 0 |  |  | 2023-09-04 21:49 | 2023-10-13 22:32
120302 | 4654 | 29007 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1330 | Execution Plan |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-07 08:00 | 2023-09-12 17:00 |  | 2023-09-07 08:00 | 2023-09-12 17:00 | 2023-09-07 08:00 | 2023-09-12 17:00 | 2023-09-07 08:00 | 2023-09-12 17:00 | 2023-09-07 08:00 | 2023-09-12 17:00 |  | PT_Normal |  |  |  |  | 4yLAyHwyokiranRBOLBxuA | U3K/AXWSoU6+/9hZ8w35ug |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:51 | 2023-10-13 22:32
120303 | 4654 | 29007 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1340 | Project Quality Plan |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-11 08:00 | 2023-09-14 17:00 |  | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-09-11 08:00 | 2023-09-14 17:00 | 2023-09-11 08:00 | 2023-09-14 17:00 |  | PT_Normal |  |  |  |  | VMc+1LMqoUeUe0lRkV1gug | mxIQeOFQ20aeyVTPttRcoQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:51 | 2023-10-13 22:32
120304 | 4654 | 29007 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1350 | HSE Plan |  | 1144 | 1144 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | EioAnRdU3kWuXRmZ1w4OAQ | EKfSV3fAI0CDH0P5zKtO8A |  |  | N | 0 | 0 |  |  | 2023-09-04 21:51 | 2023-10-13 22:32
120305 | 4654 | 29008 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1360 | Execution Plan |  | 1160 | 1160 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-13 08:00 | 2023-09-18 17:00 | 2023-09-13 08:00 | 2023-09-18 17:00 | 2023-09-13 08:00 | 2023-09-18 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 9x30S39z70+akEY0X1yO9Q | 4yLAyHwyokiranRBOLBxuA |  |  | N | 0 | 0 |  |  | 2023-09-04 21:52 | 2023-10-13 22:32
120306 | 4654 | 29008 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1370 | Project Quality Plan |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-17 08:00 | 2023-09-20 17:00 |  | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 |  | PT_Normal |  |  |  |  | Nz42OGc5H0WNRYMfYP23+w | VMc+1LMqoUeUe0lRkV1gug |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:52 | 2023-10-13 22:32
120307 | 4654 | 29008 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1380 | HSE Plan |  | 1144 | 1144 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2023-09-17 08:00 | 2023-09-20 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | PFbxmiVFRU+rA+tUyGVEWg | EioAnRdU3kWuXRmZ1w4OAQ |  |  | N | 0 | 0 |  |  | 2023-09-04 21:52 | 2023-10-13 22:32
120308 | 4654 | 29011 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1390 | Concept Plan |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-21 08:00 | 2023-09-26 17:00 |  | 2023-09-21 08:00 | 2023-09-26 17:00 | 2023-09-21 08:00 | 2023-09-26 17:00 | 2023-09-21 08:00 | 2023-09-26 17:00 | 2023-09-21 08:00 | 2023-09-26 17:00 |  | PT_Normal |  |  |  |  | dkeDznsn2kG/Cm/AKwEGtg | Nz42OGc5H0WNRYMfYP23+w |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:54 | 2023-10-13 22:32
120309 | 4654 | 29011 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1400 | General Layout |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-09-27 08:00 | 2023-10-02 17:00 |  | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-09-27 08:00 | 2023-10-02 17:00 |  | PT_Normal |  |  |  |  | aU8xIMNXP0Gs1gxeaSCgVA | PFbxmiVFRU+rA+tUyGVEWg |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:54 | 2023-10-13 22:32
120310 | 4654 | 29012 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1410 | Concept Plan |  | 32 | 32 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-03 08:00 | 2023-10-08 17:00 |  | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-09-27 08:00 | 2023-10-02 17:00 | 2023-10-03 08:00 | 2023-10-08 17:00 |  | PT_Normal |  |  |  |  | 5uJRL/1iVkqROBtm0HSE/Q | dkeDznsn2kG/Cm/AKwEGtg |  |  | N | 0 | 0 |  |  | 2023-09-04 21:55 | 2023-10-13 22:32
120311 | 4654 | 29012 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1420 | General Layout |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-03 08:00 | 2023-10-08 17:00 |  | 2023-10-03 08:00 | 2023-10-08 17:00 | 2023-10-03 08:00 | 2023-10-08 17:00 | 2023-10-03 08:00 | 2023-10-08 17:00 | 2023-10-03 08:00 | 2023-10-08 17:00 |  | PT_Normal |  |  |  |  | qBrYpHRWqkObVXzP1pxgGg | aU8xIMNXP0Gs1gxeaSCgVA |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:55 | 2023-10-13 22:32
120312 | 4654 | 29015 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1430 | IFC for Base Foundation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-09 08:00 | 2023-10-12 17:00 |  | 2023-10-09 08:00 | 2023-10-12 17:00 | 2023-10-09 08:00 | 2023-10-12 17:00 | 2023-10-09 08:00 | 2023-10-12 17:00 | 2023-10-09 08:00 | 2023-10-12 17:00 |  | PT_Normal |  |  |  |  | oQwaXgaqtU+mL1A56vAtCQ | 5uJRL/1iVkqROBtm0HSE/Q |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:57 | 2023-10-13 22:32
120313 | 4654 | 29015 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1440 | IFC for Raft Foundation |  | 784 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-28 08:00 | 2024-03-04 17:00 |  | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 |  | PT_Normal |  |  |  |  | FXos9j59CkWwYvAnEJgsaQ | qBrYpHRWqkObVXzP1pxgGg |  |  | N | 0 | 0 |  |  | 2023-09-04 21:57 | 2023-10-13 22:32
120314 | 4654 | 29016 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1450 | IFC Drawings for Base Foundation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-15 08:00 | 2023-10-18 17:00 |  | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 |  | PT_Normal |  |  |  |  | nh8tGxqI0UC3REf6Op26oA | oQwaXgaqtU+mL1A56vAtCQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 21:58 | 2023-10-13 22:32
120315 | 4654 | 29016 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1460 | IFC for Raft Foundation |  | 784 | 160 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-05 08:00 | 2024-03-10 17:00 |  | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 |  | PT_Normal |  |  |  |  | ZG0t+paiRE+PYDfG+LWSYA | FXos9j59CkWwYvAnEJgsaQ |  |  | N | 0 | 0 |  |  | 2023-09-04 21:58 | 2023-10-13 22:32
120316 | 4654 | 29018 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1470 | IFC for Columns |  | 272 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-30 08:00 | 2023-12-05 17:00 |  | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-10-15 08:00 | 2023-10-18 17:00 | 2023-11-30 08:00 | 2023-12-05 17:00 |  | PT_Normal |  |  |  |  | /Kt/Uhj7nEOQ4ZXYwp33Bg | oQwaXgaqtU+mL1A56vAtCQ |  |  | N | 0 | 0 |  |  | 2023-09-04 21:58 | 2023-10-13 22:32
120317 | 4654 | 29018 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1480 | IFC for Beams |  | 272 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-06 08:00 | 2023-12-11 17:00 |  | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-12-06 08:00 | 2023-12-11 17:00 |  | PT_Normal |  |  |  |  | 348QUjUy2ku5N9ZIPBMbjg | FXos9j59CkWwYvAnEJgsaQ |  |  | N | 0 | 0 |  |  | 2023-09-04 21:58 | 2023-10-13 22:32
120318 | 4654 | 29018 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1490 | IFC for Slab |  | 400 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-03 08:00 | 2024-01-08 17:00 |  | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2024-01-03 08:00 | 2024-01-08 17:00 |  | PT_Normal |  |  |  |  | ZMFg0aZD6kiOSQXEvPAINA | 348QUjUy2ku5N9ZIPBMbjg |  |  | N | 0 | 0 |  |  | 2023-09-04 22:00 | 2023-10-13 22:32
120319 | 4654 | 29019 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1500 | IFC for Columns |  | 304 | 160 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-12 08:00 | 2023-12-17 17:00 |  | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-12-12 08:00 | 2023-12-17 17:00 |  | PT_Normal |  |  |  |  | /CrRfSo3IEWyEujiAP044w | /Kt/Uhj7nEOQ4ZXYwp33Bg |  |  | N | 0 | 0 |  |  | 2023-09-04 22:00 | 2023-10-13 22:32
120320 | 4654 | 29019 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1510 | IFC for Beams |  | 272 | 128 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-12 08:00 | 2023-12-17 17:00 |  | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-12-12 08:00 | 2023-12-17 17:00 |  | PT_Normal |  |  |  |  | OcVYDPFQtkePfo0Vlje+EQ | 348QUjUy2ku5N9ZIPBMbjg |  |  | N | 0 | 0 |  |  | 2023-09-04 22:00 | 2023-10-13 22:32
120321 | 4654 | 29019 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1520 | IFC for Slab |  | 400 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-09 08:00 | 2024-01-14 17:00 |  | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2024-01-09 08:00 | 2024-01-14 17:00 |  | PT_Normal |  |  |  |  | 6lVVcMpEX0C0iFqZEoOS8A | ZMFg0aZD6kiOSQXEvPAINA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:00 | 2023-10-13 22:32
120322 | 4654 | 29024 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1530 | IFC for Mechanical |  | 624 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-28 08:00 | 2024-03-04 17:00 |  | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 |  | PT_Normal |  |  |  |  | Qihjto2fvUSSX47CUP7HLA | /CrRfSo3IEWyEujiAP044w |  |  | N | 0 | 0 |  |  | 2023-09-04 22:02 | 2023-10-13 22:32
120323 | 4654 | 29021 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1540 | IFC for Electrical |  | 624 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-18 08:00 | 2024-02-21 17:00 |  | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2024-02-18 08:00 | 2024-02-21 17:00 |  | PT_Normal |  |  |  |  | FTJk2yn9j0Kup++HlqGPqQ | Qihjto2fvUSSX47CUP7HLA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:02 | 2023-10-13 22:32
120324 | 4654 | 29022 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1550 | IFC for Electrical |  | 624 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-22 08:00 | 2024-02-27 17:00 |  | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2024-02-22 08:00 | 2024-02-27 17:00 |  | PT_Normal |  |  |  |  | inkS/oBFz0aQZbyGAtKAKA | FTJk2yn9j0Kup++HlqGPqQ |  |  | N | 0 | 0 |  |  | 2023-09-04 22:03 | 2023-10-13 22:32
120325 | 4654 | 29025 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1560 | IFC for Mechanical |  | 624 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-05 08:00 | 2024-03-10 17:00 |  | 2023-11-16 08:00 | 2023-11-21 17:00 | 2023-11-16 08:00 | 2023-11-21 17:00 | 2023-11-16 08:00 | 2023-11-21 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 |  | PT_Normal |  |  |  |  | YeLbPafnV022CsDBT+h0dA | Qihjto2fvUSSX47CUP7HLA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:03 | 2023-10-13 22:32
120326 | 4654 | 29028 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1570 | IFC for Plumbing |  | 656 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-28 08:00 | 2024-03-04 17:00 |  | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 |  | PT_Normal |  |  |  |  | JxJ+ac1mUU26pey3JQ+YfA | Qihjto2fvUSSX47CUP7HLA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:03 | 2023-10-13 22:32
120327 | 4654 | 29029 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1580 | IFC for Plumbing |  | 656 | 32 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-05 08:00 | 2024-03-10 17:00 |  | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 |  | PT_Normal |  |  |  |  | M4hhcVYLq0a/NuPZQ8yOog | JxJ+ac1mUU26pey3JQ+YfA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:04 | 2023-10-13 22:32
120328 | 4654 | 29032 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1590 | IFC for Fire Network |  | 656 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-28 08:00 | 2024-03-04 17:00 |  | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2024-02-28 08:00 | 2024-03-04 17:00 |  | PT_Normal |  |  |  |  | etSUatxK3EGxo/Unvgx0nQ | JxJ+ac1mUU26pey3JQ+YfA |  |  | N | 0 | 0 |  |  | 2023-09-04 22:04 | 2023-10-13 22:32
120329 | 4654 | 29033 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1600 | IFC for Fire Network |  | 656 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-05 08:00 | 2024-03-10 17:00 |  | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2024-03-05 08:00 | 2024-03-10 17:00 |  | PT_Normal |  |  |  |  | TlphWrtWQEWwcrZA/NG9mg | etSUatxK3EGxo/Unvgx0nQ |  |  | N | 0 | 0 |  |  | 2023-09-04 22:04 | 2023-10-13 22:32
120330 | 4654 | 29034 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1610 | Bulk Material |  | 624 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-11 08:00 | 2024-03-14 17:00 |  | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2024-03-11 08:00 | 2024-03-14 17:00 |  | PT_Normal |  |  |  |  | 7JZ3x0L4CUKiep5ldIYn5w | TlphWrtWQEWwcrZA/NG9mg |  |  | N | 0 | 0 |  |  | 2023-09-04 22:06 | 2023-10-13 22:32
120331 | 4654 | 29035 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1620 | Chiller |  | 760 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | vLm6cBZaAEGD/auF7PxC+w | 7JZ3x0L4CUKiep5ldIYn5w |  |  | N | 0 | 0 |  |  | 2023-09-04 22:07 | 2023-10-13 22:32
120332 | 4654 | 29036 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1630 | HVAC Material |  | 760 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | Z/alaIt+FEuB7oVYEZSqwg | vLm6cBZaAEGD/auF7PxC+w |  |  | N | 0 | 0 |  |  | 2023-09-04 22:09 | 2023-10-13 22:32
120333 | 4654 | 29039 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1640 | Layout & Marking |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-19 08:00 | 2023-10-24 17:00 |  | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 | 2023-10-19 08:00 | 2023-10-24 17:00 |  | PT_Normal |  |  |  |  | N7rMIOuGxEagpN6aBzdMuA | Z/alaIt+FEuB7oVYEZSqwg |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:10 | 2023-10-13 22:32
120334 | 4654 | 29039 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1650 | Excavation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-25 08:00 | 2023-10-30 17:00 |  | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 | 2023-10-25 08:00 | 2023-10-30 17:00 |  | PT_Normal |  |  |  |  | 4E20X1oI1k2xMomHFxpUKw | N7rMIOuGxEagpN6aBzdMuA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:11 | 2023-10-13 22:32
120335 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1660 | Leveling & Dressing & Compaction |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-10-31 08:00 | 2023-11-05 17:00 |  | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 | 2023-10-31 08:00 | 2023-11-05 17:00 |  | PT_Normal |  |  |  |  | yD53bndBkUOLUgoOy590OQ | N7rMIOuGxEagpN6aBzdMuA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:11 | 2023-10-13 22:32
120336 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1670 | PCC / Lean Concrete |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-06 08:00 | 2023-11-09 17:00 |  | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 | 2023-11-06 08:00 | 2023-11-09 17:00 |  | PT_Normal |  |  |  |  | m/42/46qmUKhvR4jZK6rbw | 4E20X1oI1k2xMomHFxpUKw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:11 | 2023-10-13 22:32
120337 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1680 | Steelfixing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-12 08:00 | 2023-11-15 17:00 |  | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 | 2023-11-12 08:00 | 2023-11-15 17:00 |  | PT_Normal |  |  |  |  | J3hMHFxiqUmiix+p+ttRyA | yD53bndBkUOLUgoOy590OQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:12 | 2023-10-13 22:32
120338 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1690 | Formwork installation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-16 08:00 | 2023-11-21 17:00 |  | 2023-11-16 08:00 | 2023-11-21 17:00 | 2023-11-16 08:00 | 2023-11-21 17:00 | 2023-11-16 08:00 | 2023-11-21 17:00 | 2023-11-16 08:00 | 2023-11-21 17:00 |  | PT_Normal |  |  |  |  | wC3TA1mmikqYV0shaTiHjA | m/42/46qmUKhvR4jZK6rbw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:12 | 2023-10-13 22:32
120339 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1700 | Pouring Concrete |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-22 08:00 | 2023-11-27 17:00 |  | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 | 2023-11-22 08:00 | 2023-11-27 17:00 |  | PT_Normal |  |  |  |  | u3LldvqmWU2yGY3Pmh0ANg | m/42/46qmUKhvR4jZK6rbw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:13 | 2023-10-13 22:32
120340 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1710 | Formwork Removal |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-11-30 08:00 | 2023-12-05 17:00 |  | 2023-11-30 08:00 | 2023-12-05 17:00 | 2023-11-30 08:00 | 2023-12-05 17:00 | 2023-11-30 08:00 | 2023-12-05 17:00 | 2023-11-30 08:00 | 2023-12-05 17:00 |  | PT_Normal |  |  |  |  | hLzDdQqL+kKfnP5mWyiMkg | J3hMHFxiqUmiix+p+ttRyA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:13 | 2023-10-13 22:32
120341 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1720 | Curing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-06 08:00 | 2023-12-11 17:00 |  | 2023-12-06 08:00 | 2023-12-11 17:00 | 2023-12-06 08:00 | 2023-12-11 17:00 | 2023-12-06 08:00 | 2023-12-11 17:00 | 2023-12-06 08:00 | 2023-12-11 17:00 |  | PT_Normal |  |  |  |  | 430qh5ENgkCbH3sKbo4aEw | wC3TA1mmikqYV0shaTiHjA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:13 | 2023-10-13 22:32
120342 | 4654 | 29040 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1730 | Bitumen Coating |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-12 08:00 | 2023-12-17 17:00 |  | 2023-12-12 08:00 | 2023-12-17 17:00 | 2023-12-12 08:00 | 2023-12-17 17:00 | 2023-12-12 08:00 | 2023-12-17 17:00 | 2023-12-12 08:00 | 2023-12-17 17:00 |  | PT_Normal |  |  |  |  | N2nIpzkXEUmAZeXfGuAOKw | 430qh5ENgkCbH3sKbo4aEw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:14 | 2023-10-13 22:32
120343 | 4654 | 29042 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1740 | Steelfixing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-18 08:00 | 2023-12-21 17:00 |  | 2023-12-18 08:00 | 2023-12-21 17:00 | 2023-12-18 08:00 | 2023-12-21 17:00 | 2023-12-18 08:00 | 2023-12-21 17:00 | 2023-12-18 08:00 | 2023-12-21 17:00 |  | PT_Normal |  |  |  |  | IE85XA3Xu06LhJ63qeolCg | J3hMHFxiqUmiix+p+ttRyA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:15 | 2023-10-13 22:32
120344 | 4654 | 29042 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1750 | Formwork installation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-24 08:00 | 2023-12-27 17:00 |  | 2023-12-24 08:00 | 2023-12-27 17:00 | 2023-12-24 08:00 | 2023-12-27 17:00 | 2023-12-24 08:00 | 2023-12-27 17:00 | 2023-12-24 08:00 | 2023-12-27 17:00 |  | PT_Normal |  |  |  |  | UsJ5nvUfEEWAzImuWqg/XA | wC3TA1mmikqYV0shaTiHjA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:15 | 2023-10-13 22:32
120345 | 4654 | 29042 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1760 | Pouring Concrete |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2023-12-28 08:00 | 2024-01-02 17:00 |  | 2023-12-28 08:00 | 2024-01-02 17:00 | 2023-12-28 08:00 | 2024-01-02 17:00 | 2023-12-28 08:00 | 2024-01-02 17:00 | 2023-12-28 08:00 | 2024-01-02 17:00 |  | PT_Normal |  |  |  |  | 1LBpVLInK02w6SUt4/7DoQ | u3LldvqmWU2yGY3Pmh0ANg |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:15 | 2023-10-13 22:32
120346 | 4654 | 29042 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1770 | Formwork Removal |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-03 08:00 | 2024-01-08 17:00 |  | 2024-01-03 08:00 | 2024-01-08 17:00 | 2024-01-03 08:00 | 2024-01-08 17:00 | 2024-01-03 08:00 | 2024-01-08 17:00 | 2024-01-03 08:00 | 2024-01-08 17:00 |  | PT_Normal |  |  |  |  | 3URxXCOeS0Clv63BUjkfag | hLzDdQqL+kKfnP5mWyiMkg |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:15 | 2023-10-13 22:32
120347 | 4654 | 29042 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1780 | Curing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-09 08:00 | 2024-01-14 17:00 |  | 2024-01-09 08:00 | 2024-01-14 17:00 | 2024-01-09 08:00 | 2024-01-14 17:00 | 2024-01-09 08:00 | 2024-01-14 17:00 | 2024-01-09 08:00 | 2024-01-14 17:00 |  | PT_Normal |  |  |  |  | kmuNYKRxAUWlA4gr2881Fg | 430qh5ENgkCbH3sKbo4aEw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:15 | 2023-10-13 22:32
120349 | 4654 | 29045 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1790 | Formwork installation |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-15 08:00 | 2024-01-18 17:00 |  | 2024-01-15 08:00 | 2024-01-18 17:00 | 2024-01-15 08:00 | 2024-01-18 17:00 | 2024-01-15 08:00 | 2024-01-18 17:00 | 2024-01-15 08:00 | 2024-01-18 17:00 |  | PT_Normal |  |  |  |  | Lq6uAfZVtEiVD7aQZhFxKQ | UsJ5nvUfEEWAzImuWqg/XA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:18 | 2023-10-13 22:32
120350 | 4654 | 29045 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1800 | Steelfixing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-21 08:00 | 2024-01-24 17:00 |  | 2024-01-21 08:00 | 2024-01-24 17:00 | 2024-01-21 08:00 | 2024-01-24 17:00 | 2024-01-21 08:00 | 2024-01-24 17:00 | 2024-01-21 08:00 | 2024-01-24 17:00 |  | PT_Normal |  |  |  |  | aQ1pktiaukusQuKK0EmlkQ | IE85XA3Xu06LhJ63qeolCg |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:18 | 2023-10-13 22:32
120351 | 4654 | 29045 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1810 | Pouring Concrete |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-25 08:00 | 2024-01-30 17:00 |  | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-01-25 08:00 | 2024-01-30 17:00 |  | PT_Normal |  |  |  |  | qhSb49aSvkaEOQD/f+ducg | 1LBpVLInK02w6SUt4/7DoQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:18 | 2023-10-13 22:32
120352 | 4654 | 29045 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1820 | Formwork Removal |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-01-31 08:00 | 2024-02-05 17:00 |  | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-01-31 08:00 | 2024-02-05 17:00 |  | PT_Normal |  |  |  |  | XudVTWBMtUqtkvegWZ0COg | 3URxXCOeS0Clv63BUjkfag |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:18 | 2023-10-13 22:32
120353 | 4654 | 29045 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1830 | Curing |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-06 08:00 | 2024-02-11 17:00 |  | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-02-06 08:00 | 2024-02-11 17:00 |  | PT_Normal |  |  |  |  | NVFLdT+uCEuP85F4G029+A | kmuNYKRxAUWlA4gr2881Fg |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:18 | 2023-10-13 22:32
120354 | 4654 | 29044 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1840 | Masonry Works |  | 160 | 160 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-11 08:00 | 2024-03-14 17:00 |  | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-03-11 08:00 | 2024-03-14 17:00 |  | PT_Normal |  |  |  |  | l5HIfvS4w0KueJ5eIO1QIA | NVFLdT+uCEuP85F4G029+A |  |  | N | 0 | 0 |  |  | 2023-09-04 22:19 | 2023-10-13 22:32
120355 | 4654 | 29047 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1850 | Plaster Inner |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-24 08:00 | 2024-03-27 17:00 |  | 2024-03-24 08:00 | 2024-03-27 17:00 | 2024-03-24 08:00 | 2024-03-27 17:00 | 2024-03-24 08:00 | 2024-03-27 17:00 | 2024-03-24 08:00 | 2024-03-27 17:00 |  | PT_Normal |  |  |  |  | 1Uxwmq+JCkmL0wUNkcFidQ | l5HIfvS4w0KueJ5eIO1QIA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:19 | 2023-10-13 22:32
120356 | 4654 | 29047 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1860 | Plaster Outer |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-28 08:00 | 2024-04-02 17:00 |  | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 |  | PT_Normal |  |  |  |  | 4hhx/BOq3kSQsCmJHysnhw | 1Uxwmq+JCkmL0wUNkcFidQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:20 | 2023-10-13 22:32
120357 | 4654 | 29048 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1870 | Screeding |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-12 08:00 | 2024-02-15 17:00 |  | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-02-12 08:00 | 2024-02-15 17:00 | 2024-02-12 08:00 | 2024-02-15 17:00 |  | PT_Normal |  |  |  |  | #NAME? | 1Uxwmq+JCkmL0wUNkcFidQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:24 | 2023-10-13 22:32
120358 | 4654 | 29048 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1880 | Tiling Work |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-18 08:00 | 2024-02-21 17:00 |  | 2024-02-18 08:00 | 2024-02-21 17:00 | 2024-02-18 08:00 | 2024-02-21 17:00 | 2024-02-18 08:00 | 2024-02-21 17:00 | 2024-02-18 08:00 | 2024-02-21 17:00 |  | PT_Normal |  |  |  |  | i/si0RcFXk+hYLVfkMRy+Q | 4hhx/BOq3kSQsCmJHysnhw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:24 | 2023-10-13 22:32
120359 | 4654 | 29049 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1890 | Formwork |  | 440 | 48 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-02 08:00 | 2024-04-07 17:00 |  | 2024-01-16 08:00 | 2024-01-21 17:00 | 2024-01-16 08:00 | 2024-01-21 17:00 | 2024-01-16 08:00 | 2024-01-21 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 |  | PT_Normal |  |  |  |  | MIiFDyveAEu3uN/HgXIVfA | #NAME? |  |  | N | 0 | 0 |  |  | 2023-09-04 22:25 | 2023-10-13 22:32
120360 | 4654 | 29049 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1900 | Steelfixing |  | 392 | 392 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-01-25 08:00 | 2024-01-30 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | QleBVZhnbUCJkjOpo24qQw | i/si0RcFXk+hYLVfkMRy+Q |  |  | N | 0 | 0 |  |  | 2023-09-04 22:25 | 2023-10-13 22:32
120361 | 4654 | 29049 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1910 | Pouring Concrete |  | 360 | 360 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-01-31 08:00 | 2024-02-05 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | /qz6+1dd3Em98RCxcT6pag | QleBVZhnbUCJkjOpo24qQw |  |  | N | 0 | 0 |  |  | 2023-09-04 22:26 | 2023-10-13 22:32
120362 | 4654 | 29049 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1920 | Formwork Removal |  | 328 | 328 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-02-06 08:00 | 2024-02-11 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | gSi5woB8/UGHxuXtHkSXqw | /qz6+1dd3Em98RCxcT6pag |  |  | N | 0 | 0 |  |  | 2023-09-04 22:26 | 2023-10-13 22:32
120363 | 4654 | 29049 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1930 | Tileing / Marble works |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-02-22 08:00 | 2024-02-27 17:00 |  | 2024-02-22 08:00 | 2024-02-27 17:00 | 2024-02-22 08:00 | 2024-02-27 17:00 | 2024-02-22 08:00 | 2024-02-27 17:00 | 2024-02-22 08:00 | 2024-02-27 17:00 |  | PT_Normal |  |  |  |  | 6KX7FsQm50yN1roBlOtYeA | gSi5woB8/UGHxuXtHkSXqw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:26 | 2023-10-13 22:32
120364 | 4654 | 29050 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1940 | Painting Inner |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-28 08:00 | 2024-04-02 17:00 |  | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 |  | PT_Normal |  |  |  |  | zGb5HyjKT0G13BfPhDcW/g | MIiFDyveAEu3uN/HgXIVfA |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:27 | 2023-10-13 22:32
120365 | 4654 | 29050 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1950 | Painting Outer |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | GrcLgh2NiUu/35xxFLuYjQ | QleBVZhnbUCJkjOpo24qQw |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:27 | 2023-10-13 22:32
120366 | 4654 | 29051 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1960 | Ceiling Work |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 3iJ20Uji2EqPXAw2l7JEsA | GrcLgh2NiUu/35xxFLuYjQ |  |  | Y | 0 | 0 |  |  | 2023-09-04 22:28 | 2023-10-13 22:32
124932 | 4654 | 29053 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1970 | Fabrication & Installation of Cable Trays/Ducts |  | 0 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-17 08:00 | 2024-03-20 17:00 |  | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-17 08:00 | 2024-03-20 17:00 | 2024-03-17 08:00 | 2024-03-20 17:00 |  | PT_Normal |  |  |  |  | 7PWXuZLi2k6aHRGa7aegbw | 3iJ20Uji2EqPXAw2l7JEsA |  |  | Y | 0 | 0 |  |  | 2023-09-08 21:24 | 2023-10-13 22:32
124933 | 4654 | 29053 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1980 | Laying of cables |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-24 08:00 | 2024-03-27 17:00 |  | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-24 08:00 | 2024-03-27 17:00 |  | PT_Normal |  |  |  |  | ROW7o9UHZESRY6cmNwy86w | 7PWXuZLi2k6aHRGa7aegbw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:24 | 2023-10-13 22:32
124934 | 4654 | 29053 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A1990 | Installation of DB's & Fixtures |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-03-28 08:00 | 2024-04-02 17:00 |  | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-27 08:00 | 2024-04-01 17:00 | 2024-03-28 08:00 | 2024-04-02 17:00 |  | PT_Normal |  |  |  |  | FBmEHz8SL0a/Uv+6aLuWMg | ROW7o9UHZESRY6cmNwy86w |  |  | N | 0 | 0 |  |  | 2023-09-08 21:25 | 2023-10-13 22:32
124935 | 4654 | 29053 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2000 | Glading & Terminantion / Connections |  | 8 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-02 08:00 | 2024-04-07 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | VyuNSqB3Gk+CidCJ7MmFOQ | FBmEHz8SL0a/Uv+6aLuWMg |  |  | N | 0 | 0 |  |  | 2023-09-08 21:25 | 2023-10-13 22:32
124936 | 4654 | 29054 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2010 | Fabrication & Installation & Insulation of Ducts |  | 72 | 72 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-03-21 08:00 | 2024-03-26 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | zvVrviT8wk+fDJlsRAmYfQ | 7PWXuZLi2k6aHRGa7aegbw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:29 | 2023-10-13 22:32
124937 | 4654 | 29054 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2020 | Installation / Erection of Piping |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | HgljWMYQNUCpH99tlpN6Ew | ROW7o9UHZESRY6cmNwy86w |  |  | N | 0 | 0 |  |  | 2023-09-08 21:29 | 2023-10-13 22:32
124938 | 4654 | 29054 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2030 | Fixtures installations |  | 1224 | 1216 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | Q8RM28SgnUiO6BnZPsmZCA | FBmEHz8SL0a/Uv+6aLuWMg |  |  | N | 0 | 0 |  |  | 2023-09-08 21:29 | 2023-10-13 22:32
124940 | 4654 | 29055 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2040 | Fabrication railing for staircase |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | PxaGas0yKkyYFGOMSwBxgw | zvVrviT8wk+fDJlsRAmYfQ |  |  | N | 0 | 0 |  |  | 2023-09-08 21:31 | 2023-10-13 22:32
124941 | 4654 | 29055 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2050 | Erection of Railing |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | w4aJgIx5eU2Ybjj34aijpg | HgljWMYQNUCpH99tlpN6Ew |  |  | N | 0 | 0 |  |  | 2023-09-08 21:31 | 2023-10-13 22:32
124942 | 4654 | 29055 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2060 | Painting Works |  | 1224 | 1216 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 7XFMxjB1GkyQav3mO9EC9Q | Q8RM28SgnUiO6BnZPsmZCA |  |  | N | 0 | 0 |  |  | 2023-09-08 21:31 | 2023-10-13 22:32
124944 | 4654 | 29056 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2070 | Fabrication and installation of FW piping |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | OSKJ3V2ZSkCesiJ7hRiydg | PxaGas0yKkyYFGOMSwBxgw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:34 | 2023-10-13 22:32
124945 | 4654 | 29056 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2080 | Installation of Firehouse |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 0Jd9yQGr0Umw5av7CJQU+w | w4aJgIx5eU2Ybjj34aijpg |  |  | N | 0 | 0 |  |  | 2023-09-08 21:34 | 2023-10-13 22:32
124946 | 4654 | 29056 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2090 | Installation of High pressure Pump |  | 1224 | 1216 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | ED3sfMEgdku5pFXu5qzsIw | 7XFMxjB1GkyQav3mO9EC9Q |  |  | N | 0 | 0 |  |  | 2023-09-08 21:34 | 2023-10-13 22:32
124947 | 4654 | 29057 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2100 | Installation of frame & Rail & Counter weight |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | FfzcoKhrPUGf0sr0g2GlLw | OSKJ3V2ZSkCesiJ7hRiydg |  |  | N | 0 | 0 |  |  | 2023-09-08 21:38 | 2023-10-13 22:32
124948 | 4654 | 29057 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2110 | Installation of Motor |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | JKDqwSJne0mh8+FbvJpYhQ | 0Jd9yQGr0Umw5av7CJQU+w |  |  | N | 0 | 0 |  |  | 2023-09-08 21:38 | 2023-10-13 22:32
124949 | 4654 | 29057 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2120 | Interior finishing |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | HCZfpn8dJUuHRd6/6QwzRA | ED3sfMEgdku5pFXu5qzsIw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:38 | 2023-10-13 22:32
124950 | 4654 | 29057 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2130 | Connections |  | 1224 | 1216 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 4ErIceTnAU+n6oarDv+zXw | HCZfpn8dJUuHRd6/6QwzRA |  |  | N | 0 | 0 |  |  | 2023-09-08 21:42 | 2023-10-13 22:32
124951 | 4654 | 29058 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2140 | Punlisting for Ground Floor |  | 1224 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | gzMtYFUpPUqR2zG4kRNBbg | FfzcoKhrPUGf0sr0g2GlLw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:43 | 2023-10-13 22:32
124952 | 4654 | 29058 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2150 | Punlisting for Basement |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | dMZ2JTPa70yuB6IQTfnhBg | JKDqwSJne0mh8+FbvJpYhQ |  |  | N | 0 | 0 |  |  | 2023-09-08 21:43 | 2023-10-13 22:32
124954 | 4654 | 29059 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2160 | Testing of Services |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | g8PjewmxYEC7B9f185fPKw | FfzcoKhrPUGf0sr0g2GlLw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:45 | 2023-10-13 22:32
124955 | 4654 | 29059 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2170 | Closing of A type Punch Points |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | bRF6Da5jHEaLkr4/OeTLYg | JKDqwSJne0mh8+FbvJpYhQ |  |  | N | 0 | 0 |  |  | 2023-09-08 21:45 | 2023-10-13 22:32
124956 | 4654 | 29060 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2180 | Commissioning of GF |  | 1224 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | prg2ONzUIkWk28SmTKRl0Q | HCZfpn8dJUuHRd6/6QwzRA |  |  | N | 0 | 0 |  |  | 2023-09-08 21:45 | 2023-10-13 22:32
124957 | 4654 | 29060 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2190 | Commissioning of Basement |  | 1224 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | kdQ58VUaFE2xmZ0VNcDzuQ | 4ErIceTnAU+n6oarDv+zXw |  |  | N | 0 | 0 |  |  | 2023-09-08 21:45 | 2023-10-13 22:32
124958 | 4654 | 29061 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2200 | Submission of Design Package (As-Built) |  | 1224 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | +0kbjuxqL0i49MUDYRB6Vg | prg2ONzUIkWk28SmTKRl0Q |  |  | N | 0 | 0 |  |  | 2023-09-08 21:49 | 2023-10-13 22:32
124959 | 4654 | 29061 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2210 | Submission of Final Dossier |  | 1224 | 1224 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | 2GFIotXvCEa/ZWK6e7bPIA | kdQ58VUaFE2xmZ0VNcDzuQ |  |  | N | 0 | 0 |  |  | 2023-09-08 21:49 | 2023-10-13 22:32
124960 | 4654 | 29062 | 6773 | 0 | N | 1 | N | N | CP_Drtn | TT_Task | DT_FixedDUR2 | TK_NotStart | A2220 | Demobilization |  | 1224 | 0 | 32 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  |  |  | 2024-04-03 08:00 | 2024-04-08 17:00 |  | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2023-09-03 08:00 | 2023-09-06 17:00 | 2024-04-03 08:00 | 2024-04-08 17:00 |  | PT_Normal |  |  |  |  | DkIIgS+gMUK4z7q3W0fFUQ | 2GFIotXvCEa/ZWK6e7bPIA |  |  | N | 0 | 0 |  |  | 2023-09-08 21:50 | 2023-10-13 22:32

## ACTVTYPE (hidden)
actv_code_type_id | actv_short_len | seq_num | actv_code_type | proj_id | wbs_id | actv_code_type_scope | export_flag
1645 | 14 | 100 | Ground Floor 111111111111 | 4654 |  | AS_Project
1646 | 7 | 0 | (New Activity Code) | 4654 |  | AS_Project

## PROJWBS (hidden)
wbs_id | proj_id | obs_id | seq_num | est_wt | proj_node_flag | sum_data_flag | status_code | wbs_short_name | wbs_name | phase_id | parent_wbs_id | ev_user_pct | ev_etc_user_value | orig_cost | indep_remain_total_cost | ann_dscnt_rate_pct | dscnt_period_type | indep_remain_work_qty | anticip_start_date | anticip_end_date | ev_compute_type | ev_etc_compute_type | guid | tmpl_guid | plan_open_state
28990 | 4654 | 540 | 1 | 1 | Y | N | WS_Open | BL-001 | Office Building Works |  | 28989 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Er6ULtXdtEeHYSy1KyM0PQ
28991 | 4654 | 540 | 1 | 5 | N | N | WS_Open | 1 | Project Start / Initation Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Slu1BTOzmE+tCbBMwdcOZQ
28992 | 4654 | 540 | 101 | 3 | N | N | WS_Open | 2 | Documnets Submission Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | OQIX/8KBv0eqYyyhWECQuA
28993 | 4654 | 540 | 201 | 25 | N | N | WS_Open | 3 | Engineering & Design Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | sAmJdDhEfU2zHrCc2u1lyg
28994 | 4654 | 540 | 301 | 10 | N | N | WS_Open | 4 | Procurement Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | H/jRKV7s7UyDoYEe7oF7Kw
28995 | 4654 | 540 | 401 | 50 | N | N | WS_Open | 5 | Construction Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Jgd3knT5+UmdMgwL97PQ7A
28996 | 4654 | 540 | 501 | 5 | N | N | WS_Open | 6 | Comissioning Phase |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | AZ+KxCuhgEWMdJmlf/jM4g
28997 | 4654 | 540 | 601 | 2 | N | N | WS_Open | 7 | Project Close Out |  | 28990 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | UlOmAbILTUGn1Ixutky7fw | AZ+KxCuhgEWMdJmlf/jM4g
28998 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Letter of Award |  | 28991 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | qQVAJstGeEqAgYhrha8ItA
28999 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Kick of Meeting |  | 28991 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | KEAOxFVhzUSv8RCDkqVGGg
29000 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 3 | Project Milestones |  | 28991 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | MxLAU/ToZEu65WS/LHwOpw
29001 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Start Milstones |  | 29000 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | kvCXH/kLkk2Cta76Z7iWag
29002 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Finish Milstones |  | 29000 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | g8A61WVgwk+VZgE5xTvXYQ
29003 | 4654 | 540 | 3 | 1 | N | N | WS_Open | 3 | Payment Milstones |  | 29000 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | K/URdNnBtUiInuxXd2FEzQ
29004 | 4654 | 540 | 301 | 1 | N | N | WS_Open | 4 | Moblization Phase |  | 28991 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | QZo/0E0HGUOGlUlM3oEP4w
29005 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Labor Resoures |  | 29004 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Mv70tU9PXUSfpXKmgfX/SQ
29006 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Non-Labor Resources |  | 29004 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 1PDEqTV8w0qJD0dvRbvJ+Q
29007 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Preparation & Submission |  | 28992 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | TdUOER+ggU+dgeEGJJtsXA
29008 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Approval |  | 28992 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | m5PiXinHAEmaH87iDH4zjg
29009 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Coceptual Design |  | 28993 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 3TVZw4KrxEiU+jm+4XezTQ
29011 | 4654 | 540 | 0 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29009 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Upq/wqodtEeeSyM6OIJXmQ | TdUOER+ggU+dgeEGJJtsXA
29012 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 2 | Approval |  | 29009 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Y/NYCkXGWE+JHT3TmpWH7g | m5PiXinHAEmaH87iDH4zjg
29013 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Detailed Design |  | 28993 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | B5yPggAedk+i1t8VCsfMnQ
29014 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Sub-Structure |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | mmig+GzR8Eu9VxYUo9RqqA
29015 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29014 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | oxjRN/2b/kKKRNVGMBC9+w | Upq/wqodtEeeSyM6OIJXmQ
29016 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Approval |  | 29014 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | tFKliFRmaEqG3NVXT/4oGg | Y/NYCkXGWE+JHT3TmpWH7g
29017 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Super Structure |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | sQhs5mYpBE2RECp/tshUwQ | mmig+GzR8Eu9VxYUo9RqqA
29018 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29017 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | doAINKFTmUiCtRpfuwbnaQ | oxjRN/2b/kKKRNVGMBC9+w
29019 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Approval |  | 29017 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Elgn9ZmFGUGZCpwb3bhhYA | tFKliFRmaEqG3NVXT/4oGg
29020 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 3 | Electrical |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | Z/FNw+U3sUSTHEhyYTnqPg | sQhs5mYpBE2RECp/tshUwQ
29021 | 4654 | 540 | 0 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29020 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | sT4MS+kMjkO2sOUMLZH4CA | doAINKFTmUiCtRpfuwbnaQ
29022 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 2 | Approval |  | 29020 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | heKyBTAWrES4xb/yV4pzDA | Elgn9ZmFGUGZCpwb3bhhYA
29023 | 4654 | 540 | 301 | 1 | N | N | WS_Open | 4 | Mechanical Drawings |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | N70Id9PiT0esg9dvjV2G6w | Z/FNw+U3sUSTHEhyYTnqPg
29024 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29023 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | usnqKyY2ikCOGRePXCFmPQ | sT4MS+kMjkO2sOUMLZH4CA
29025 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Approval |  | 29023 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | jKd/Nhi7S02ca68SA9F8dg | heKyBTAWrES4xb/yV4pzDA
29027 | 4654 | 540 | 401 | 1 | N | N | WS_Open | 5 | Plumbing Drawings |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 2n/jVI7jU0mEQ3e7TCQrwA | N70Id9PiT0esg9dvjV2G6w
29028 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29027 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | jK5Bhs1Xd0alicph5ZhgqA | usnqKyY2ikCOGRePXCFmPQ
29029 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Approval |  | 29027 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | hWVVkLkxykCq8kfJl3v8LQ | jKd/Nhi7S02ca68SA9F8dg
29031 | 4654 | 540 | 501 | 1 | N | N | WS_Open | 6 | Fire Network Drawings |  | 29013 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | dYN/lpolGEmGXMBCXOf4AQ | 2n/jVI7jU0mEQ3e7TCQrwA
29032 | 4654 | 540 | 0 | 1 | N | N | WS_Open | 3 | Preparation & Submission |  | 29031 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 6Zwhp86w80C6YDhym6KcoA | jK5Bhs1Xd0alicph5ZhgqA
29033 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 2 | Approval |  | 29031 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | zIQz9yhoNEqSkTUuwmUI/w | hWVVkLkxykCq8kfJl3v8LQ
29034 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Local Purchase |  | 28994 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | wxF4oD8QXkmMBHHVX6ebWg
29035 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Forign Procurement |  | 28994 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 0HGtrO35A0yKc85hDFpfqw
29036 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 3 | Longlead Items |  | 28994 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | zYL7rj41M02olyI0MFGNrQ
29037 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Civil Works |  | 28995 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | WWsI6l5b3EyX2gv1B1SFSw
29038 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Sub-Structure |  | 29037 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | zizcuQMmBUCt71qVH2eZBA
29039 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Excavation |  | 29038 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | k6jpgloUnEmebD6Wrs06rA
29040 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Foundation |  | 29038 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | auFQ2CLlu0SHYRaV36zbRQ
29041 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 3 | Super Structure |  | 29037 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | IYmojPh7Pkar62EJBaDbVQ | zizcuQMmBUCt71qVH2eZBA
29042 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Coulmn & Beams |  | 29041 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | x7qZht4ckUK20BsnZvyQFw | k6jpgloUnEmebD6Wrs06rA
29044 | 4654 | 540 | 3 | 1 | N | N | WS_Open | 3 | Masonary Works |  | 29041 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | G91sMYPwSUaCebLSbPE81g
29045 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 4 | Slab Works |  | 29041 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | JNlcznVXS0KEmNPk6sbRsA
29046 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 2 | Finishing Works |  | 29037 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | QHT6MJmRL0qhNr6EKQzQBg
29047 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Walls |  | 29046 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | /1vD5qEcz0ipHtOcs8s6Sg
29048 | 4654 | 540 | 2 | 1 | N | N | WS_Open | 2 | Floor |  | 29046 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | K5RrzqE6xE2JJRYnPN3RDw
29049 | 4654 | 540 | 3 | 1 | N | N | WS_Open | 3 | Staircase |  | 29046 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | fudh4hqmVkikDI5onFsLGQ
29050 | 4654 | 540 | 4 | 1 | N | N | WS_Open | 4 | Painting |  | 29046 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | #NAME?
29051 | 4654 | 540 | 5 | 1 | N | N | WS_Open | 5 | Cieling |  | 29046 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | hMz7Gk9GRkCeF+qQjEiRiQ
29052 | 4654 | 540 | 301 | 1 | N | N | WS_Open | 6 | Services |  | 29037 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | EHCwGpWH9Eutn2JEiwACyg
29053 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Electrical |  | 29052 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | SYeBECa0nUu9Ti2Y97c/mA
29054 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Plumbing |  | 29052 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | QoyiLz9C7EOwGyqabEoQeQ
29055 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 3 | Mechanical |  | 29052 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | OolPhjjLNE+RelJC+7QZCg
29056 | 4654 | 540 | 301 | 1 | N | N | WS_Open | 4 | Fire Netwrok |  | 29052 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | PQje4u4W8UCufYQf1JvZ1Q
29057 | 4654 | 540 | 401 | 1 | N | N | WS_Open | 5 | Lift Works |  | 29052 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | aKmt+brQnEufaq+EYcumiA
29058 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Punchlisting / Snags |  | 28996 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | sDEi9MOB9UCv03S5JsmpBw
29059 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Pre-Comissioning |  | 28996 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | CevPNzPpiEe8OAANBGfwlw
29060 | 4654 | 540 | 201 | 1 | N | N | WS_Open | 3 | Comissioning |  | 28996 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 69Ah4SQ3KEmq1XSdta6BgQ
29061 | 4654 | 540 | 1 | 1 | N | N | WS_Open | 1 | Final Documentation |  | 28997 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | UWPYrN1+O0qQoRfMh28gSg
29062 | 4654 | 540 | 101 | 1 | N | N | WS_Open | 2 | Demoblization |  | 28997 | 6 | 0.88 | 0 | 0 | [5 empty] | EC_Cmp_pct | EE_Rem_hr | 1QJbnE8r7UyeRP7KsOyp4g

## SCHEDOPTIONS (hidden)
schedoptions_id | proj_id | sched_outer_depend_type | sched_open_critical_flag | sched_lag_early_start_flag | sched_retained_logic | sched_setplantoforecast | sched_float_type | sched_calendar_on_relationship_lag | sched_use_expect_end_flag | sched_progress_override | level_float_thrs_cnt | level_outer_assign_flag | level_outer_assign_priority | level_over_alloc_pct | level_within_float_flag | level_keep_sched_date_flag | level_all_rsrc_flag | sched_use_project_end_date_for_float | enable_multiple_longest_path_calc | limit_multiple_longest_path_calc | max_multiple_longest_path | use_total_float_multiple_longest_paths | key_activity_for_multiple_longest_paths | LevelPriorityList
1 | 4654 | SD_Both | N | Y | Y | N | FT_FF | rcal_Predecessor | Y | N | 0 | N | 5 | 25 | N | Y | Y | Y | N | Y | 10 | Y |  | priority_type,ASC_BY_FIELD/ASC

## CALENDAR (hidden)
clndr_id | default_flag | clndr_name | proj_id | base_clndr_id | last_chng_date | clndr_type | day_hr_cnt | week_hr_cnt | month_hr_cnt | year_hr_cnt | rsrc_private | clndr_data
6773 | N | Asif Project |  |  | 2023-09-16 00:00 | CA_Base | 8 | 40 | 176 | 2112 | N | (0¦¦CalendarData()( (0¦¦DaysOfWeek()( (0¦¦1()( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦2()( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦3()( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦4()( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦5()( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦6()()) (0¦¦7()()))) (0¦¦VIEW(ShowTotal¦N)()) (0¦¦Exceptions()( (0¦¦0(d¦45172)( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)()))) (0¦¦1(d¦45263)( (0¦¦0(s¦08:00¦f¦12:00)()) (0¦¦1(s¦13:00¦f¦17:00)())))))))

## PROJECT (hidden)
proj_id | fy_start_month_num | rsrc_self_add_flag | allow_complete_flag | rsrc_multi_assign_flag | checkout_flag | project_flag | step_complete_flag | cost_qty_recalc_flag | batch_sum_flag | name_sep_char | def_complete_pct_type | proj_short_name | acct_id | orig_proj_id | source_proj_id | base_type_id | clndr_id | sum_base_proj_id | task_code_base | task_code_step | priority_num | wbs_max_sum_level | strgy_priority_num | last_checksum | critical_drtn_hr_cnt | def_cost_per_qty | last_recalc_date | plan_start_date | plan_end_date | scd_end_date | add_date | last_tasksum_date | fcst_start_date | def_duration_type | task_code_prefix | guid | def_qty_type | add_by_name | web_local_root_path | proj_url | def_rate_type | add_act_remain_flag | act_this_per_link_flag | def_task_type | act_pct_link_flag | critical_path_type | task_code_prefix_flag | def_rollup_dates_flag | use_project_baseline_flag | rem_target_link_flag | reset_planned_flag | allow_neg_act_flag | sum_assign_level | last_fin_dates_id | fintmpl_id | last_baseline_update_date | cr_external_key | apply_actuals_date | location_id | last_schedule_date | loaded_scope_level | export_flag | new_fin_dates_id | baselines_to_export | baseline_names_to_export | next_data_date | close_period_flag | sum_refresh_date | trsrcsum_loaded | sumtask_loaded
4654 | 1 | Y | Y | Y | N | Y | N | N | Y | . | CP_Drtn | BL-001 |  |  |  |  | 6773 |  | 1000 | 10 | 10 | 2 | 500 |  | 0 | 0 | 2023-09-01 08:00 | 2023-08-01 |  | 2024-04-08 17:00 | 2023-09-01 |  |  | DT_FixedDUR2 | A | 6XKz4q+e40OePXn/gfzyKg | QT_Hour | PLANNING-P6 |  |  | COST_PER_QTY | N | Y | TT_Task | Y | CT_TotFloat | Y | Y | Y | Y | N | N | SL_Taskrsrc |  | 1 |  |  |  |  | 2023-10-13 22:32 | 7 | Y | [5 empty] | 1899-12-30 00:00

## UDFTYPE (hidden)
udf_type_id | table_name | udf_type_name | udf_type_label | logical_data_type | super_flag | indicator_expression | summary_indicator_expression | export_flag
987 | TASK | user_field_987 | Duration - Reduction | FT_FLOAT_2_DECIMALS | N

## OBS (hidden)
obs_id | parent_obs_id | guid | seq_num | obs_name | obs_descr
540 |  |  | 0 | Enterprise | <html> <head>  </head> <body bgcolor=""#ffffff""> Enterprise </body></html>

## FINTMPL (hidden)
fintmpl_id | fintmpl_name | default_flag
1 | Calendar | Y

## CURRTYPE (hidden)
curr_id | decimal_digit_cnt | curr_symbol | decimal_symbol | digit_group_symbol | pos_curr_fmt_type | neg_curr_fmt_type | curr_type | curr_short_name | group_digit_cnt | base_exch_rate
1 | 2 | $ | . | , | #1.1 | (#1.1) | US Dollar | USD | 3 | 1
13 | 2 | £ | . | , | #1.1 | (#1.1) | Pound Sterling | GBP | 3 | 0.6186
14 | 2 | ¥ | . | , | #1.1 | (#1.1) | Japanese Yen | JPY | 3 | 91.2708
15 | 2 | € | . | , | #1.1 | (#1.1) | Euro | EUR | 3 | 0.68971
16 | 2 | ¥ | . | , | #1.1 | (#1.1) | Chinese Yuan Renminbi | CNY | 3 | 6.825
17 | 2 | $ | . | , | #1.1 | (#1.1) | Canadian Dollar | CAD | 3 | 1.0376
18 | 2 | RUB | . | , | #1.1 | (#1.1) | Russian Ruble | RUB | 3 | 0.033948
19 | 2 | $ | . | , | #1.1 | (#1.1) | Argentine Peso | ARS | 3 | 3.7911
20 | 2 | $b | . | , | #1.1 | (#1.1) | Bolivian Boliviano | BOB | 3 | 7.5708
21 | 2 | R$ | . | , | #1.1 | (#1.1) | Brazilian Real | BRL | 3 | 1.7665
22 | 2 | $ | . | , | #1.1 | (#1.1) | Chilean Peso | CLP | 3 | 507.58
23 | 2 | $ | . | , | #1.1 | (#1.1) | Columbian Peso | COP | 3 | 1957.74
24 | 2 | $ | . | , | #1.1 | (#1.1) | Guyanese Dollar | GYD | 3 | 202.95
25 | 2 | Gs | . | , | #1.1 | (#1.1) | Paraguayan Guarani | PYG | 3 | 4640
26 | 2 | S/. | . | , | #1.1 | (#1.1) | Peruvian Nuevo Sol | PEN | 3 | 2.7244
27 | 2 | $ | . | , | #1.1 | (#1.1) | Surinamese Dollar | SRD | 3 | 2.8
28 | 2 | Bs | . | , | #1.1 | (#1.1) | Venezuelan Bolivar Fuerto | VEF | 3 | 2.1446
29 | 2 | $U | . | , | #1.1 | (#1.1) | Uruguayan Peso | UYU | 3 | 21.247